Metrics Handbook

Table of Contents

1	Introduction	4

1.1	Purpose	4

1.2	Scope	4

1.3	Intended Audience	6

1.4	Definition	6

2	Metrics	6

2.1	People metrics	6

2.2	Process metrics	6

2.3	Business metrics	6

3	Functional Metrics	6

3.1	Project metrics	6

3.2	Process metrics	7

3.3	Product metrics	7

4	Operational Definitions for Metrics	7

4.1	People Metrics	7

4.1.1)	Project Team Skill Index	7

4.2	Process Metrics	9

4.2.1)	Process Compliance Index percentage	9

4.3	Business Metrics	10

4.2.2)	Return on Investment percentage	10

5	Operational Definitions for Functional Metrics	11

5.1	Project Metrics	11

5.1.1)	Effort Variance	11

5.1.2)	Schedule Variance	12

5.1.3)	Effort distribution by phase	13

5.1.4)	Schedule Delay	14

5.1.5)	Test Case Coverage percentage	15

5.1.6)	Requirements Stability Index percentage	16

5.2	Process Metrics	18

5.2.1)	Requirements Productivity	18

5.2.2)	Design Productivity	19

5.2.3)	Coding & Unit testing Productivity	20

5.2.4)	System & Integration testing Productivity	21

5.2.5)	Overall productivity	22

5.2.6)	Test Case Execution Productivity	23

5.2.7)	Test case review Defect Density	24

5.2.8)	Test Case Re-Use Percentage	26

5.2.9)	Test Effectiveness percentage	27

5.3	Product Metrics	28

5.3.1)	Rejected Defect Percentage	28

5.3.2)	Defect Severity Index (DSI)	29

5.3.3)	Phase Containment Effectiveness Percentage	30

5.3.4)	Defect Queue Status	32

5.3.5)	Closed Defects Ratio	33

5.3.6)	Requirement Defect Density	34

5.3.7)	Design Defect Density	35

5.3.8)	Coding & Unit Testing Defect Density	36

5.3.9)	Internal Defect Density	37

5.3.10)	Delivered Defect Density	39

5.3.11)	Overall Defect Density	40

5.3.12)	Defect Removal Efficiency	41

Introduction

Metrics is a standard method of measurement that quantifies the results. Software metrics are numerical data related to software development life cycle. Metrics strongly support software project management activities.

Purpose

The purpose of this document is to provide operational definitions for metrics to be used in projects. Guidelines are provided for easy understanding of metrics, their usage in software development lifecycle quantitative management and in taking informed go, no-go decisions.

Metrics support in following key project management areas:

1. Plan - help in estimates for resource planning, scheduling and costing

2. Monitor and control – helps in tracking the current status of the project activities

3. Report – helps in providing unambiguous and comprehensive status update across multiple roles in the organization

4. Process Improvement – help in identifying the areas that need improvement based on targets and goals

Scope

The scope of the metrics is limited to the development lifecycles.

ARTERIA Standard metrics are identified and confirmed using the Goal, Question, and Metric (GQM) Methodology described in the SEI manual “Goal Driven Software Measurement”.

GQM is a top-down approach to establish a goal-driven measurement system for software development, in that the team starts with organizational goals, defines measurement goals, poses questions to address the goals, and identifies metrics that provide answers to the questions.  GQM defines a measurement model on three levels as illustrated in the figure below:

GQM can be applied to all life-cycle products, processes, and resources, and is well aligned with the organizational environment.  The approach was developed by Dr. Victor Basili and colleagues during the 1980s in conjunction with their work at the NASA Software Engineering Laboratory (SEL), was refined during the 1990s, and now, serves as the foundation framework for many measurement initiatives.  It is an appropriate means to achieve reliable empirical data and knowledge about the organization’s software practices to drive systematic process improvement.  In that context, it is particularly useful for the following purposes:

- Understanding and base lining an organization’s software practices

- Guiding and monitoring software processes

- Assessing new software engineering technologies

- Evaluating and certifying improvement activities

Although the primary focus of the practice is goal-driven metrics definition, the approach also addresses data collection, analysis and interpretation and packaging experiences for use in future initiatives. These activities are equally as important as defining the metrics because they guide how the data is actually used.

In summary, GQM is goal-driven method for developing and maintaining a meaningful metrics program that is based on three levels, Goals, Questions and Metrics. The approach uses metrics to improve the software development process (and its resulting software products) while maintaining alignment with organization business and technical goals.

For ARTERIA, the top level goals are as follows:

- To improve customer satisfaction (C-SAT).

- To improve profit margin (%).

Refer to ARTERIA organizational GQM:

In order to minimize metrics data collection effort, only base measures are collected by the project’s metrics. These measures are collected on the project closure form or at the completion of each change request, enhancement and release. Metrics data is also collected at defined project milestones in the same form and the only the relevant sections are filled.

Intended Audience

Project Owners, Test Managers, Test Leads, Project Team Leads, Senior Software Engineers, Business Analysts, Development owners and Test Engineers

Definition

Development Project: This term is used to indicate set of development activities that is part of software development. A development project is one of the many projects managed by ARTERIA.

Leadership: This term is used to indicate the roles in an organization that are responsible for taking strategic decision (budgeting, release decision etc.) with respect to the project health.

Metrics

Metrics are divided into 4 categories which an Organization should capture for establishing Measurement system.

- People metrics which captures the metrics related to people or human resources.

- Process metrics captures the process implementation metrics.

- Project metrics captures the project implementation metrics.

- Business metrics captures the benefits of implementation of system across the organization

People metrics

- Project Team Skill Index

Process metrics

- Process Compliance Index percentage

Business metrics

- Return on Investment percentage

Functional Metrics

Project metrics

- Effort Variance

- Schedule Variance

- Schedule Delay

- Effort distribution by phase

- Test Case Coverage percentage

- Requirements Stability Index

Process metrics

- Requirements Productivity

- Design Productivity

- Coding & Unit Testing Productivity

- System Testing and Integration Testing Productivity

- Productivity

- Test Case Execution Productivity

- Test case review defect density

- Test Case Re-Use percentage

- Test Effectiveness percentage

Product metrics

- Rejected Defect Percentage

- Phase Containment Effectiveness Percentage (Defect Containment)

- Defect Severity Index (DSI)

- Defect Queue Status

- Closed Defects Ratio

- Requirement Defect Density

- Design review  Defect Density

- CUT Defect density

- Internal Defect density

- Delivered defect density

- Overall Defect Density

- Defect Removal Efficiency

Operational Definitions for Metrics

People Metrics

### Project Team Skill Index

| Purpose | To identify and analyze the overall rating of specific project area skill across the organization. - Leadership team: This metric is used by Leadership team to determine the average skill level of resources and skill adequacy of organization. - Operational team: It helps the team to determine the average number of skills resources have in particular area. |
| --- | --- |
| Measurement Objective | - To have proper distribution of the skills across different project areas in an organization - To know the competency of the organization across different project areas |
| Base Measures | Skills Baseline value Average of the project team skill index |
| Data Type | Discrete data type |
| Metric Equation | (Skills Baseline value – Average of the project team skill index) |
| Unit of Measure | Index on scale of 1-5 where 1 – Beginner, 2 – Intermediate, 3- Experienced, 4 – Advanced, 5 – Master 0 & < 0 - Team skills meets expected skills 0 – 2, Team skills are below expectation > 2 Critical |
| Frequency of Data Collection | Quarterly / Release wise / dependent on organizational needs |
| Data Source | Competency matrix with assessment |
| Required in Reports | Metrics dashboard |
| Inference | Lesser value for particular project area triggers - Team skills meets expected skills and suitable for the project Higher value for particular project area triggers- Team skills are below expectation should be improved through some trainings. |
| Related Metrics | NA |
| Example | Data available: Baseline value for the skill set is defined =4 3 project resources are working in an insurance project Resource 1 – SQL rating - 2 (on scale of 1 to 5) Resource 2 – SQL rating - 3 (on scale of 1 to 5) Resource 3 – SQL rating - 4 (on scale of 1 to 5) Project team skill index( for SQL) = (4- ((2+3+4)/3) = 1(some training should be required) |
| Representation | Bar graph |

Process Metrics

### Process Compliance Index percentage

| Purpose | To check for the rigor of process implementation in the projects and in the organization as a whole. - Leadership Team: This index helps understand the adherence to defined processes by projects at an organizational level and in driving corrective measures. - Operational Team: It helps to assess team in implementing the process adherence |
| --- | --- |
| Measurement Objective | - To improve process compliance within the project |
| Base Measures | - Checklist driven measurement - Effectiveness weighed by the degree of process compliance - Degree of process compliance varies as Effective, Partially effective, Not effective, Not practiced |
| Data type | Continuous Data type |
| Metric Equation | Average of rating given to each questionnaire with respect to its applicable value Number of process fulfilled PCI = ---------------------------------------------------------------------- * 100 Total number of applicable process checklist points Rating will be measured, for effective 1, for partially effective 0.67, for not effective 0.33 and not practiced will be considered as 0 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Monthly /Release wise / dependent on Organizational needs |
| Data Source | PCI Checklist |
| Required in Reports | Metrics dashboard |
| Inference Note | - If PCI is <= 79% then the team needs to take action on the partially effective, not effective and not practiced. - If PCI is between 80%-89% then the project processes are unstable and an immediate action to be taken to ensure more stable processes. - If PCI is >= 90% then it implies the process are been sustained in the project, and team need to look for the continuous improvements. |
| Related Metrics | NA |
| Example | Data Available: Total Number of Checklist points = 50 (with score 250) Number of process fulfilled = 40 (with score 220) 220 PCI = -------- * 100 250 = 88% ( This means its partially effective) |
| Representation | Line chart & Bar graph |

Business Metrics

### Return on Investment percentage

| Purpose | ROI evaluates the efficiency of an investment or to measure the profitability of an investment - Leadership team: It helps management in terms of what is the year on year benefit out of the investment. - Operational team: This helps operational team in determining the investment in terms of acquiring product or tool. |
| --- | --- |
| Measurement Objective | - To check the benefit from the Investment |
| Base Measures | Gain from investment Total invested amount |
| Data Type | Continuous data type |
| Metric Equation | (Gain from investment /Total Invested Amount) * 100 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Yearly/Half yearly |
| Data Source | ROI report |
| Required in Reports | Metrics dashboard |
| Inference | - Less - If an investment has low ROI then operational strategy needs to revisit. - More - If an investment shows high ROI then it’s consider as stable or profitable investment |
| Related Metrics | All Utilization Metrics |
| Example | Data Available: Amount of Investment on a particular product= $1,000 Earned in a year= $1,250. Gain =$1250 - $ 1000 = $ 250. ROI = ($ 250 / $1,000) * 100 = 25%. |
| Representation | Line graph |

Operational Definitions for Functional Metrics

Project Metrics

Project metrics provide an overview of the progress of the project. Typically variations in effort, schedule and scope are monitored using these metrics

### Effort Variance

| Purpose | To identify and analyze the variance between planned/estimated effort and the actual effort and take appropriate actions to minimize the variance. - Leadership team: This Metric helps management in understanding the effort planned and expended at project level. It helps in decision making for taking appropriate actions. - Operational team: This metric helps the team to estimate future effort and to revise the existing estimation model. It helps to minimize the variance. |
| --- | --- |
| Measurement Objective | - Facilitates taking timely corrective or preventive action - To improve estimation process - To improve predictability |
| Base Measures | Planned effort in person hours Actual effort in person hours |
| Data Type | Continuous Data type |
| Metric Equation | (((Actual effort - Planned effort)/Planned effort) * 100) |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise / dependent on project needs |
| Data Source | PTMS & WBS |
| Required in Reports | - Project Status reports - Metrics dashboard |
| Inference | - Any variance, positive or negative, reveals the need for revisiting the estimation process - This metric should be used along with schedule variance - If schedule variance is negligible and effort variance is high - shows incorrect estimation or low productivity |
| Related Metrics | - Schedule variance - Test case execution productivity |
| Example | Data Available: Planned/Estimated hours to complete a project =1000 hours Actual hours to complete the task = 1100 hours Effort Variance = (((Actual effort - Planned effort)/Planned effort) * 100) = ((1100-1000)/1000)*100 = 10% |
| Representation | Line graph |

### Schedule Variance

| Purpose | To identify and analyze the variance between planned schedules and actual schedules to take appropriate actions for minimizing the variance. - Leadership team: It helps in decision making and to determine the capability of on-time delivery - Operational team: It helps to determine the capability of on-time delivery and estimation. |
| --- | --- |
| Measurement Objective | - Facilitate taking timely corrective or preventive action. - To improve planning process - To improve predictability |
| Base Measures | Planned End date Actual End date Planned Start date |
| Data Type | Continuous Data type |
| Metric Equation | {(Actual end date – Planned end date)/ ((Planned end date – Planned Start date)}*100 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise / dependent on project needs |
| Data Source | PTMS & WBS |
| Required in Reports | - Project Status reports - Metrics dashboard |
| Inference Note | - Any variance, positive or negative, reveals the need for revisiting the planning process - Use this metric along with effort variance - If effort variance is negligible and schedule variance is high - shows improper planning or delay in dependent task completion such as unplanned outages, delay in delivery of build from development team. |
| Related Metrics | - Effort variance |
| Example | Data Available: Planned Start Date: 1-Mar-09 Planned End Date: 31-Mar-09 Actual Start Date: 2-Mar-09 Actual End Date: 1-Apr-09 Schedule Variance = ((Actual end date – Planned end date)/(Planned end date – Planned start date)) * 100 = {(1-Apr-09) – (31-Mar-09)}/{( 31-Mar-09) – (1-Mar-09) }*100 = (1 / (30)) * 100 = (1/3) *100 = 3.3% |
| Representation | Line graph |

### Effort distribution by phase

| Purpose | To understand the effective utilization of resources across multiple project activities/phases. - Leadership team: In case across the projects more efforts are being spent in non-productive activities then leadership may invest in tools or process improvements. - Operational team: The team will be able to identify the areas where the effort is being spent as a team and ensure non-productive activities are kept to minimal. |
| --- | --- |
| Measurement Objective | - Facilitates taking timely corrective or preventive action - To improve productivity - To improve planning |
| Base Measures | Effort spent (phase based – project initiation, project planning, project monitoring and tracking, discovery, solution design, solution implementation, project closure) |
| Data Type | Continuous data type |
| Metric Equation | (Sum of effort spent in a phase for release/Total effort spent in a release) |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Dependent on release needs & project needs |
| Data Source | PTMS |
| Required in Reports | - Project Status reports - Metrics dashboard |
| Inference Note | If the effort being spent in non-productive activities is high and for productive activity is low, management should take appropriate decision to balance it. |
| Related Metrics | Effort variance |
| Example | Data available: Total effort spent in the project in release 1: 1000 person hours Effort distribution by phase: (50/1000), (200/1000), (150/1000), (150/1000), (200/1000), (200/1000), (50/1000) : 5%, 20%, 15%, 15%, 20%, 20%, 5% |
| Representation | Pie chart |

### Schedule Delay

| Purpose | To monitor the number of days the schedule is delayed from the planned completion date. - Leadership team: It helps to determine the capability of on-time delivery. - Operational team: It helps in decision making for re-scheduling the milestone dates |
| --- | --- |
| Measurement Objective | - Track on-time delivery - Facilitate timely corrective/preventive action |
| Base Measures | Planned Completion Date Actual Completion Date |
| Data Type | Continuous Data type |
| Metric Equation | (Actual End Date – Planned End Date) |
| Unit of Measure | Number of days |
| Frequency of Data Collection | Release wise / dependent on project needs |
| Data Source | PTMS & WBS |
| Required in Reports | - Project Status reports - Metrics dashboard |
| Inference Note | - Greater than zero, indicates - Delay in planned deliverables, re-planning is required or analyze risks. - Less than zero indicates - Bad estimations; Improved services using automation/process improvements etc. |
| Related Metrics | - Effort Variance - Schedule Variance |
| Example | Data Available: Planned Start Date: 1-Mar-09 Planned End Date: 31-Mar-09 Actual Start Date: 2-Mar-09 Actual End Date: 1-Apr-09 Schedule Delay = Actual End Date – Planned End Date) = (1-Apr-09 - 31-Mar-09) = 1day |
| Representation | Line graph |

### Test Case Coverage percentage

| Purpose | To identify / determine the test coverage with respect to requirements - Leadership team: Leadership team takes go-no go decision based on the Test coverage. - Operational team: It provides the overall picture of where we are in test case creation and test case execution in terms of requirements. If there is a deviation from the projects specific target set, corrective/preventive action should be taken. E.g.: Re planning on Effort, Schedule, Resources, etc |
| --- | --- |
| Measurement Objective | - To facilitate taking go, no-go decisions - To ensure all the key requirements are covered during testing |
| Base Measures | No. of requirements No. of requirements with test cases |
| Data Type | Continuous data type |
| Metric Equation | ((No. of requirements with test cases/ Total No. of requirements)*100) |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise/ dependent on project needs |
| Source | Test case sheet |
| Required in Reports | - Project Status reports - Metrics dashboard |
| Inference Note | If requirements test coverage is less, then we can interpret that the test cases are not created / executed against all requirements. Note: If ad-hoc testing is being done then this metric cannot be implemented. |
| Related Metrics | NA |
| Example | Data Available: Total number of requirements = 120 Total number of requirement with mapped test cases = 92 Percentage of test coverage = (92/120)*100 = 77 % |
| Representation | Line chart |

### Requirements Stability Index percentage

| Purpose | To calculate the total number of requirements that were planned at the beginning of the test cycle and how many changes have crept in during the later phases. - Leadership team: This metric provides an overall representation of requirements in terms of systematize, manage, and track changes to the originally specified requirements for a project. - Operational team: This metric helps the team to track Requirement Stability and also helps to identify any deviation from the baseline in requirement stability. |
| --- | --- |
| Measurement Objective | - For improved estimation as changing requirements result in re-estimates - To ensure better testing approach, as testing may be impacted due to frequent changes to requirements. |
| Base Measures | Planned requirements - No. of requirements that are planned initially. Changed requirements - No. of changed requirements (additions/modifications/deletions) |
| Data Type | Continuous Data type |
| Metric Equation | ((Planned requirements / (Planned requirements + Changed requirements)) * 100) |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise or dependent on project needs |
| Data Source | BRS, SRS, Change request log |
| Required in Reports | - Project Status reports - Metrics dashboard |
| Inference Note | - If requirement stability index is nearer to 100%, implies that no changes have been made to the requirements - If requirement stability index is lower than 80%, then too many changes are happening to requirements. Implementation should be stopped and requirements should be baseline for the project |
| Related Metrics | Inversely related to - Defect severity index |
| Example | Data Available: Planned requirements identified and approved for the project = 77 Changed requirements = 25 (Addition, Changes and Deletion) Requirement Stability Index = (77/(77+25)) * 100 = 75 % |
| Representation | Line graph |

Process Metrics

### Requirements Productivity

| Purpose | - To understand the overall performance of the resources working on the Requirement phase. - Leadership team: Helps to analyze the effort spend on Requirement phase (gathering & elicitation). - Operational team: It helps the team to enhance the requirement phase productivity by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve estimation process based on the productivity - To assess productivity levels of the Requirement Gathering Teams |
| Base Measures | Total No. of hours spent in requirement phase Size of the project |
| Data Type | Continuous Data type |
| Metric Equation | ( Size of the project(FP))/ Total No. of hours spent in requirement phase) Here : Requirement phase includes Requirement prepration & analysis, Requirement review, Requirement rework |
| Unit of Measure | FP / Person hour |
| Frequency of Data Collection | Release wise/ Dependent on project needs |
| Data Source | PTMS Function points analysis |
| Required in Reports | Project status report |
| Inference Note | - Requirements productivity is less than baseline triggers corrective actions like raising resource skill levels or increase the number of resources etc. - In case Requirements productivity is higher than the baseline, it means: - Skill level of the requirement gathering & elicitation team is higher than needed. - Revisit the estimation process - Revisit the requirement process. |
| Related Metrics | Overall Productivity |
| Example | Data Available: Total No. of hrs. spent in requirement phase = 100hrs Size of projects = 300 FP Requirement productivity = 300/100 = 3FP/hr |
| Representation | Line graph |

### Design Productivity

| Purpose | - To understand the overall performance of the resources working on the Design phase. - Leadership team: Helps to analyze the effort spend on Design phase (HLD & LLD). - Operational team: It helps the team to enhance the design phase productivity by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve estimation process based on the productivity - To assess productivity levels of the Design Teams |
| Base Measures | Total No. of hours spent in design phase Size of the project |
| Data Type | Continuous Data type |
| Metric Equation | ( Size of the project(FP))/ Total No. of hours spent in design phase) Here : Design phase includes Design prepration & analysis, Design review, Design rework |
| Unit of Measure | FP/ Person hour |
| Frequency of Data Collection | Release wise / Dependent on project needs |
| Data Source | PTMS Function points analysis |
| Required in Reports | Project status report |
| Inference Note | - Design productivity is less than baseline triggers corrective actions like raising resource skill levels or increase the number of resources etc. - In case Design productivity is higher than the baseline, it means: - Skill level of the design team is higher than needed. - Revisit the estimation process - Revisit the design process. |
| Related Metrics | Overall Productivity |
| Example | Data Available: Total No. of hrs spent in design phase = 70hrs Size of projects = 300 FP Design productivity = 300/70 = 4.28/FP |
| Representation | Line graph |

### Coding & Unit testing Productivity

| Purpose | - To understand the overall performance of the resources working on the CUT phase. - Leadership team: Helps to analyze the effort spend on CUT phase (coding & unit testing). - Operational team: It helps the team to enhance the CUT phase productivity by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve estimation process based on the productivity - To assess productivity levels of the CUT Teams |
| Base Measures | Total No. of hours spent in CUT phase Size of the project |
| Data Type | Continuous Data type |
| Metric Equation | (Size of the project(FP)/ Total No. of hours spent in CUT phase) Here : CUT phase includes CUT prepration & analysis, CUT review, CUTrework |
| Unit of Measure | FP / Person hour |
| Frequency of Data Collection | Release wise / Dependent on project needs |
| Data Source | PTMS Function points analysis |
| Required in Reports | Project status report |
| Inference Note | - CUT productivity is less than baseline triggers corrective actions like raising resource skill levels or increase the number of resources etc. - In case CUT productivity is higher than the baseline, it means: - Skill level of the CUT team is higher than needed. - Revisit the estimation process - Revisit the Coding & unit testing process. |
| Related Metrics | Overall Productivity |
| Example | Data Available: Total No. of hrs spent in CUT phase = 130 hrs Size of projects = 300 FP CUT productivity = 300/130 = 2.30 FP/Hr |
| Representation | Line graph |

### System & Integration testing Productivity

| Purpose | - To understand the overall performance of the resources working on the system & integration testing phase. - Leadership team: Helps to analyze the effort spend on SIT phase (System & integration testing). - Operational team: It helps the team to enhance the SIT phase productivity by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve estimation process based on the productivity - To assess productivity levels of the SIT Teams |
| Base Measures | Total No. of hours spent in SIT phase Size of the project |
| Data Type | Continuous Data type |
| Metric Equation | (Size of the project(FP) /Total No. of hours spent in SIT phase) Here : SIT phase includes SIT prepration & analysis, SIT review, SIT rework |
| Unit of Measure | FP/ Person hour |
| Frequency of Data Collection | Release wise / Dependent on project needs |
| Data Source | PTMS Function points analysis |
| Required in Reports | Project status report |
| Inference Note | - SIT productivity is less than baseline triggers corrective actions like raising resource skill levels or increase the number of resources etc. - In case SIT productivity is higher than the baseline, it means: - Skill level of the SIT team is higher than needed. - Revisit the estimation process - Revisit the Testing process. |
| Related Metrics | Overall Productivity |
| Example | Data Available: Total No. of hrs spent in SIT phase = 80 hrs Size of projects = 300 FP SIT productivity = 300/80 = 3.75 FP/ hr |
| Representation | Line graph |

### Overall productivity

| Purpose | - To understand the overall performance of the resources working in the Project. - Leadership team: Helps to analyses the effort spend on the project. - Operational team: It helps the team to enhance the project productivity by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve estimation process based on the productivity - To assess productivity levels of the resources under the project. |
| Base Measures | Total No. of hours spent in a project Size of the project |
| Data Type | Continuous Data type |
| Metric Equation | ( Size of the project(FP)/ Total No. of hours spent in a project) Here : Project includes Requirement phase, Design phase, CUT phase, SIT phase. |
| Unit of Measure | FP / Person hour |
| Frequency of Data Collection | Release wise / Dependent on project needs |
| Data Source | PTMS Function points analysis |
| Required in Reports | Project status report |
| Inference Note | - Overall productivity is less than baseline triggers corrective actions like raising resource skill levels or increase the number of resources etc. - In case Overall productivity is higher than the baseline, it means: - Skill level of the projects resources is higher than needed. - Revisit the estimation process. |
| Related Metrics | NA |
| Example | Data Available: Total No. of hrs spent in a project = 380 hrs Size of projects = 300 FP Overall productivity = 300/380 = 0.78 FP/hr |
| Representation | Line graph |

### Test Case Execution Productivity

| Purpose | - To understand the overall performance of the testing team - To evaluate the rate at which test cases are executed - Leadership team: Helps to analyze the effort spend on test case execution. - Operational team: It helps the team to enhance the test case execution productivity by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve estimation process based on the productivity - To assess productivity levels of the testing teams |
| Base Measures | No. of test cases executed No. of person hours spent in test case execution |
| Data Type | Continuous Data type |
| Metric Equation | (Number of test cases executed / Effort spent in test case execution) |
| Unit of Measure | Number of test cases / person hour |
| Frequency of Data Collection | Release wise or dependent on project needs |
| Data Source | PTMS |
| Required in Reports | SIT Report |
| Inference Note | - Test case execution productivity is less than baseline triggers corrective actions like raising resource skill levels or increase the number of resources etc. - In case test case execution productivity is higher than the baseline, it means: - Skill level of the testing team is higher than needed - Revisit the estimation process - Revisit the test execution process. |
| Related Metrics | NA |
| Example | Data Available: No. of test cases executed = 225 No. of person hours spent = 30 Test case execution productivity = 225/30 = 7.5 TCs/Hrs |
| Representation | Line graph |

### Test case review Defect Density

| Purpose | To analyze the overall efficiency of the testing team in a project and to improve quality of the project and review process. - Leadership Team: It helps leadership team to determine the understanding of the team on functionality and/or domain for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain/ application technical skills to come up with less test case review defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the testing team on a functionality and domain of a projects. |
| Base Measures | Number of test case review defects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of defects in a test case review)/(total number of test case reviewed) |
| Unit of Measure | No. of defects per test case |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Test case Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the test case review defect density in a project to achieve its business goals, - Less test case review defect density indicates better work by the work product authored team. - Less test case review defect density indicates reviewers are not efficient in detecting test case review defects from the work product authored. - Higher test case review defect density indicates team should improve their understanding on product/domain and functionality skills by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of test case review defects in a project = 60 defects Total no of test case reviewed = 800 Test case review Defect Density = (60/800) = 0.075 defects/test case Inferences: almost 7 defects per 100 test case. |
| Representation | Pie Chart |

### Test Case Re-Use Percentage

| Purpose | To improve productivity and to reduce authoring cost and time. - Leadership Team: It would help the leadership team to analyze the amount of cost and time saved by reusing the test cases in similar module/application with same functionality. - Operational team: It helps operational team to determine the amount of test cases are re-used in other modules/applications with similar functionality |
| --- | --- |
| Measurement Objective | - To reduces the time that is spent on test design |
| Base Measures | Number of reusable test cases |
| Data Type | Continuous Data type |
| Metric Equation | ((Total number of test cases reused / Total number of test cases created)*100 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise /Project end or dependent on organizational needs. |
| Data Source | Test cases Document |
| Required in Reports | Metrics dashboard |
| Inference | Testers should build test cases around reusable test patterns that should be common to a large number of applications: - Higher number of metric outcome infers reduction in re-work which interns reduce the cost and time - Lower number of metric outcome infers increase in cost, time and needs to author new test cases |
| Related Metrics | Effort distribution by phase |
| Example | Data available: Total number of test cases created = 50 Total number of test cases reused = 5 Test Case Re-Use Percentage = (5/50)*100 = 10 % |
| Representation | Pie Graph |

### Test Effectiveness percentage

| Purpose | - To compare between defects found by test team vs. defects found by client/user - Leadership Team: This metric provide overall figures on defects slipped into customer’s environment(UAT) - Operational team: It helps to assess the competency of the test teams |
| --- | --- |
| Measurement Objective | - To ensure higher client satisfaction by reducing defect creep into production - To assess the quality of testing |
| Base Measures | - Total defects found by test team (Defects accepted by client) - Number of defects found by client/user(UAT) |
| Data Type | Continuous Data type |
| Metric Equation | ((Defects found by testing team / (Defects found by internal team + Defects found by user)) * 100 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise/ Test cycle/ phase based or dependent on the project priorities |
| Data Source | Bugzilla, UAT defect log |
| Required in Reports | - SIT report - Project Status report |
| Inference Note | - The test effectiveness should be closer to 100%. If no defects slipped into production, then test effectiveness will be 100% - Lower test effectiveness implies we need to improve testing processes, test coverage, tester skills. |
| Related Metrics | - Test case effectiveness - Phase containment effectiveness |
| Example | Data Available: Total Number of defects found by test team = 59 Total Number of defects found by Client(UAT) = 3 Test Effectiveness= ((59/(59+3)) * 100 = 95 % |
| Representation | Line graph |

Product Metrics

### Rejected Defect Percentage

| Purpose | The purpose of this metric is to measure the accuracy of the defects detected and To ensure the understanding of the testers of the application under test - Leadership team: It helps in determining the rate of rejection. - Operational Team: It helps to ensure valid defects are logged by testers. |
| --- | --- |
| Measurement Objective | - To reduce multiple iterations of rework or clarifications regarding the defects, in turn reducing the cycle time - To assess the understanding of requirements by the testers and the developers |
| Base Measures | Percentage |
| Data Type | Continuous Data type |
| Metric Equation | ((Total number of Defects rejected per release / Total number of Defects detected per release ) *100) |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise or dependent on project priorities |
| Data Source | Bugzilla |
| Required in Reports | SIT report |
| Inference Note | - High percentage of rejected defects implies - the defects are not clear enough to understand, hence defect reporting should be improved and/or Defects are not reproducible by developers - Test team needs to understand the product requirements in a clear way. |
| Related Metrics | NA |
| Example | Data Available: Total no. of defects detected in release 1 = 230 Rejected defects in release 1 = 46 Rejected defect percentage = (46/230)*100 = 20% |
| Representation | Line graph |

### Defect Severity Index (DSI)

| Purpose | To provide a direct measurement of the quality of the product. It determines the quality of the product at the time of release, which helps to take decision for releasing of the product. - Leadership team: Helps measuring the quality of the product. Provides a direct measurement of the quality of the product. - Operational team: Helps analyzing the results and come up with an action plan to resolve the issue in specific timelines. |
| --- | --- |
| Measurement Objective | • Assess the quality of the application • Facilitate making informed. Go, no-go decision |
| Base Measures | DS1 - # of open defects at Severity1 (Blocker) DS2 - # of open defects at Severity1 (Critical) DS3 - # of open defects at Severity2 (Major) DS4 - # of open defects at Severity3 (Minor) |
| Data Type | Continuous Data type |
| Metric Equation | ((DS1*5) + (DS2*3) + (DS3*2) + (DS4*1)/ (DS1+DS2+DS3+DS4) Note: The rating given to severity: Blocker – 5 Critical – 3, Major –2, Minor – 1 |
| Unit of measure | Index on scale of 1 – 5 |
| Frequency of Data Collection | Release wise or dependent on project needs |
| Data Source | Bugzilla. |
| Required in Reports | SIT Report |
| Inference | • In case of high defect severity index we can infer that the product contains more defects, which includes critical defects. Based on this the client can take go, no-go decision (Whether the build can be released into production or not) • In case of low DSI the product can be pronounced as stable to the extent it is tested. |
| Related Metric | Open defect count in that build |
| Example | Data Available: Total no. of defects = 75 No. of Blocker defects = 20 No. of Critical defects = 15 No. of Major defects = 0 No. of Minor defects = 40 DSI = ((20*5)+(15*3)+(40*1))/(20+15+40) = 185/75 = 2.46 |
| Representation | Bar graph |

### Phase Containment Effectiveness Percentage

| Purpose | This metric gives an indication of the review / testing process within a phase. Any defect leaked to the next phase indicates that the test / review mechanism for that phase is not adequate. Phase containment Effectiveness is calculated at Phase level. - Leadership team: It helps to ensure the quality of testing and review. If there is a deviation from the Baseline or the projects specific target set, corrective/preventive action to be taken. - Operational team: Helps uncover more defects in testing, re-review the work product. To make the team more pro-active in order to catch the defects in same phase it-self. |
| --- | --- |
| Measurement Objective | To measures the effectiveness of the review or testing in the particular phase of the project. |
| Base Measures | 1 - Number of defects detected in the particular phase 2 - Sum of defects injected till that particular phase 3 - Number of defects detected in the previous phase |
| Data Type | Continuous Data type |
| Metric Equation | ((Number of defects detected in that particular phase) / ((Sum of defects injected till that particular phase) – (Number of defects already detected in the previous phase)))* 100 |
| Unit of Measure | Defect Percentage |
| Frequency of Data Collection | Release wise/ phase based or dependent on the project priorities |
| Data Source | Bugzilla , Defect analysis sheet |
| Required in Reports | Project Status Report |
| Inference Note | This metric measures the efficiency of review & testing in identifying all the issues within that phase. Low Phase Containment effectiveness ratio: - A high leakage rate indicates that the process of review / testing carried out needs to be looked upon. - Define and Implement more rigorous ways of capturing defects with in the phase. - Testing & reviews are not effective - Test approach was not correct - Resources were not skilled |
| Related Metrics | NA |
| Example | Data Available: Defects detected in SIT = 12 defects Defects detected in Req=10 defects Defects detected in Design =7 defects Defect detected in Cut =13 defects Defects detected in UAT =10 defects Total number of defects injected in Req, Design & CUT are 52 defects(i.e Req=20, Design=17, CUT=15) Phase containment effectiveness(SIT) = [12/(52-30) ] X 100 = 55% |
| Representation | Line graph |

### Defect Queue Status

| Purpose | To identify the number of defects held with Dev, QA & Unaddressed/Blank (Assign to status in tool could be Blank) based on defect status. - Leadership team: This metric gives an idea to leadership on the outstanding defects with development team and QA team. - Operational team: The operational team realizes the urgency to push any outstanding defects they are holding. |
| --- | --- |
| Measurement Objective | To manage the defect resolution process |
| Base Measures | Count of defect with various status DS1 - # of defects in QA DS2 - # of defects in Dev DS3 - # of defects not addressed |
| Data Type | Discrete Data type |
| Metric Equation | No. of Defects assigned to QA (defects with status Fixed) No. of defects assigned to DEV ( Defect status with New + Reopen + Wont fixed) No. of defect unaddressed - Defect status with Invalid + Duplicate + work for me + Closed) |
| Unit of measure | Count |
| Frequency of Data Collection | Release wise or dependent on project needs |
| Data Source | Bugzilla |
| Required in Reports | SIT Report |
| Inference | Higher number in respective queue indicates the action should be taken in order to fix the defects. |
| Related Metric | None |
| Example | Data available: Total number of Defects assign to QA = 10 (Defect status with Fixed) No of Defects assign to Dev = 15 (Defect status with New + Reopen + wont fixed ) # of Defects with Status “New” = 5 # of Defects with Status “Wont fixed” = 4 # of Defects with Status “Reopen” =6 No. of defects Unassigned = 2 (The defects which are logged but rejected) |
| Representation | Line graph |

### Closed Defects Ratio

| Purpose | This metric can be used to predict the quality of the product considering the number of closed defects. It gives information on the quantity (%) of closed defects against total defects posted throughout the test execution phase. - Leadership team: Will be keen to understand how many critical defects are closed by testing team. - Operational team: This metric helps operational team to focus on critical and major defects and bring them to closure soon. |
| --- | --- |
| Measurement Objective | To compare the defects at the end of each test cycle/release as closed defects Vs. total defects |
| Base Measures | Closed Defects - # of Closed Defects at the end of cycle/release Total no# of defects |
| Data Type | Continuous Data type |
| Metric Equation | Closed Defects Ratio: Calculated based on total number of defects against Closed Defects. = [(Total No. of Closed Defects)/( Total No. of Defects)]*100 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise or dependent on project needs |
| Data Source | Bugzilla |
| Required in Reports | SIT Report |
| Inference Note | This metric helps in analysis of product quality and in making decisions on release, High number of open defects will call for delay. |
| Related Metrics | None |
| Example | Data available: Data collected on Week ending 2: Open defect count = 15 (20 %) Closed defect count = 60 (80 %) Total number of defects: 75 |
| Representation | Line graph |

### Requirement Defect Density

| Purpose | To analyze the overall efficiency of the Requirement gathering team in a project and to improve quality of the project. - Leadership Team: It helps leadership team to determine the understanding of the team on functionality and/or domain for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain or application to come up with less review defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the requirement gathering team in a project. |
| Base Measures | Number of Requirements review defects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of defects in a Requirements review)/(size of the project) |
| Unit of Measure | No. of defects per Function point |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the requirement defect density in a project to achieve its business goals, - Less requirements defect density indicates better work by the work product authored team. - Less requirement s defect density indicates reviewers are not efficient in detecting defects from the work product authored. - Higher requirements defect density indicates team should improve their understanding on product/domain by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of requirements defects in a project = 60 defects size of project = 300 FP Defect Density = (60/300) = 0.20 defects/FP |
| Representation | Pie Chart |

### Design Defect Density

| Purpose | To analyze the overall efficiency of the Design team in a project and to improve quality of the project. - Leadership Team: It helps leadership team to determine the understanding of the team on functionality and/or domain for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain/ application technical skills to come up with less review defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the design team in a project. |
| Base Measures | Number of design review defects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of defects in a design review)/(size of the project) |
| Unit of Measure | No. of defects per Function point |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the design defect density in a project to achieve its business goals, - Less design defect density indicates better work by the work product authored team. - Less design defect density indicates reviewers are not efficient in detecting design defects from the work product authored. - Higher design defect density indicates team should improve their understanding on product/domain and technical skills by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of design defects in a project = 80 defects size of project = 300 FP Defect Density = (80/300) = 0.27 defects/FP |
| Representation | Pie Chart |

### Coding & Unit Testing Defect Density

| Purpose | To analyze the overall efficiency of the development team in a project and to improve quality of the project. - Leadership Team: It helps leadership team to determine the understanding of the team on functionality, domain & technical skills for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain, application and technical skills to come up with less review and testing defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the project team in a project. |
| Base Measures | Number of Code review defects unit testing defects size of projects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of unit testing defects + code review defects in a project)/(size of the project) |
| Unit of Measure | No. of defects per Function point |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Bugzilla(testing defects) & Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the CUT defect density in a project to achieve its business goals, - Less CUT defect density indicates better work by the work product authored & development team. - Less CUT defect density indicates reviewers & unit testers are not efficient in detecting defects from the work product authored and against the codes. - Higher Cut defect density indicates team should improve their understanding on product/ domain and technical skills by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of CUT defects in a project = 60 defects size of project = 300 FP Defect Density = (60/300) = 0.20 defects/FP |
| Representation | Pie Chart |

### Internal Defect Density

| Purpose | To analyze the overall efficiency of the Testing team in a project and to improve quality of the project. - Leadership Team: It helps leadership team to determine the understanding of the testing team on functionality, domain & testing skills for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain, application & testing skills to come up with less review and testing defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the testing team in a project. |
| Base Measures | Number of SIT defects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of SIT defects in a project)/(size of the project) |
| Unit of Measure | No. of defects per Function point |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Bugzilla (testing defects) & Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the defect density in a project to achieve its business goals, - Less Internal defect density indicates better work by the work product authored & development team. - Higher Internal defect density indicates reviewers are not efficient in detecting defects from the work product authored and against the codes. - Higher Internal defect density indicates team should improve their understanding on product/domain and coding skills by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of SIT defects in a project = 80defects size of project = 300 FP Defect Density = (100/300) = 0.34 defects/FP |
| Representation | Pie Chart |

### Delivered Defect Density

| Purpose | To analyze the overall efficiency of the Testing team in a project and to improve quality of the project. - Leadership Team: It helps leadership team to determine the understanding of the testing team on functionality, domain & testing skills for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain, application & testing skills to come up with less review and testing defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the testing team in a project. |
| Base Measures | Number of UAT defects Size of projects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of UAT defects in a project)/(size of the project) |
| Unit of Measure | No. of defects /Function point |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Bugzilla (testing defects) & Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the defect density in a project to achieve its business goals, - Less Delivered defect density indicates better work by the work product authored & development team. - Less Delivered defect density indicates reviewers & testers are efficient in detecting defects from the work product authored and against the codes. - Higher Delivered defect density indicates team should improve their understanding on product/domain and testing skills by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of UAT defects in a project = 100defects size of project = 300 FP Defect Density = (100/300) = 0.34 defects/FP |
| Representation | Pie Chart |

### Overall Defect Density

| Purpose | To analyze the overall efficiency of the team in a project and to improve quality of the project. - Leadership Team: It helps leadership team to determine the understanding of the team on functionality and/or domain for delivering high quality product\project - Operational team: Based on the results operational team can take actions by joining the trainings to understand the domain or application to come up with less review and testing defects. |
| --- | --- |
| Measurement Objective | - To understand the accuracy of the project team in a project. |
| Base Measures | Number of defects |
| Data Type | Continuous Data type |
| Metric Equation | (Total number of defects in a project)/(size of the project) Here :Total defects includes (Internal defects + users defects) |
| Unit of Measure | No. of defects per Function point |
| Frequency of Data Collection | Release wise or Project end. |
| Data Source | Bugzilla(testing defects) & Review defect log |
| Required in Reports | - Metrics dashboard - Project status report |
| Inference | Organization can act based on the defect density in a project to achieve its business goals, - Less defect density indicates better work by the work product authored & development team. - Less defect density indicates reviewers & testers are not efficient in detecting defects from the work product authored and against the codes. - Higher defect density indicates team should improve their understanding on product/domain by undergoing trainings and also needs to improve work product authoring skills. |
| Related Metrics | NA |
| Example | Data available: Total No. of defects in a project = 300 defects size of project = 300 FP Defect Density = (300/300) = 1defects/FP |
| Representation | Pie Chart |

### Defect Removal Efficiency

| Purpose | - To understand the overall performance of the resources working on the project in terms of resolving the defects. - Leadership team: Helps to analyze the extent to which project team is able to resolve the defects in a projects and level of technical competency. - Operational team: It helps the team to enhance the functional & technical skills by taking suitable measures to meet the baseline. |
| --- | --- |
| Measurement Objective | - To improve the technical & functional capabilities based on the DRE. |
| Base Measures | No. of defects in injected in a project (Internal defects + users defects) No. of defect finally resolved |
| Data Type | Continuous Data type |
| Metric Equation | Total no. of defects in SIT phase/ (Total no. of SIT defects+Total no. of UAT defects)*100 |
| Unit of Measure | Percentage |
| Frequency of Data Collection | Release wise / Dependent on project needs |
| Data Source | Bugzilla, Review defect log & client defect log |
| Required in Reports | Project status report |
| Inference Note | - DRE is less than baseline triggers corrective actions like raising resource technical & functional skill levels - In case DRE is higher than the baseline, it means: - Skill level of the team is higher than needed. |
| Related Metrics |  |
| Example | Data Available: Total no. of SIT defects =30 Total no. of UAT defects=5 DRE = (30/(30+5))*100 = 85.7 % |
| Representation | Line graph |