Configuration Management Guidelines

Revision History

| Version Number | Creation/ Revision Date | Prepared /Updated By | Reviewed By | Approved By | Change Description |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 14.06.2023 | Rajashree M. | Jayanta C. | Jayanta C. | Baseline the Guidelines |

Table of Contents

1	Purpose	4

2	Scope	4

3	Intended Audience	4

4	Acronyms and Abbreviations	4

5	Description	4

5.1	Configuration Management	4

5.2	Change Control Board	8

5.3	Configuration Identification	8

5.3.1	Project Baselines	8

5.3.2	Identification of Configurable Items	9

5.3.3	Customer Supplied Items	11

5.4	Naming Convention	12

5.4.1	Naming Convention for Project Documents	12

5.4.2	Naming Convention for Tailored template or checklist	12

5.4.3	Naming Convention for New template or checklist	12

5.5	Storing Configuration	13

5.6	Version Control and Promotion	13

5.7	Build Configuration	14

5.8	Base lined Configuration	14

5.9	Configuration Status Accounting	15

5.10	Configuration Auditing	16

5.11	Configuration Management Milestone	17

5.12	Configuration Management Tools	17

6	Stakeholder’s Matrix	18

7	Glossary	18

Purpose

The purpose of this document is to provide an understanding of configuration management and help project in implementing Configuration management. This Guideline is meant to assist the project manager in carrying out the configuration management activities in the project. It describes in details the baselines, configurable items (CIs) and how to identify them.

This guideline aims at giving an overall idea of various controls involved in CM.

Scope

This guideline applies to all projects and products of CMS

Intended Audience

- Project Manager

- Configuration Controller

- SQA coordinator

- Test Function Owner

- Delivery Head

Acronyms and Abbreviations

| Abbreviation | Expansion |
| --- | --- |
| CC | Configuration Controller |
| CCB | Change Control Board |
| DH | Delivery Head |
| DO | Development Owner |
| PM | Project Manager |
| REV | Reviewer |
| SQA | Software Quality Assurance |
| TST | Tester |
| SA | Systems Administrator |
| MOM | Minutes of Meeting |

Description

Configuration Management

Configuration management is how a project ensures that the contents of systems are known, that changes are authorized, and that the documentation accurately describes the system. Configuration management is both a management and a technical discipline that involves nearly everyone in a project either actively, as performers of configuration management activities, or passively, as recipients of configuration management information.

The essence of configuration management is control—identification of what needs to be controlled, controlling those items through change management and configuration control functions, reporting metrics to help understand the status of the items under control, and finally, auditing to ensure that the control processes are working effectively.

Configuration management includes the following concepts:

- Configuration-managed items—Items that are directly involved with the system and are therefore part of baselines. All aspects of configuration management apply to these items. These comprise:

  - The deliverable system at all levels, from configuration items down to configuration units.

  - Related documents—Documents that define configuration items and components, such as negotiated agreements, specifications, charts, drawings, code, and change orders.

  - Development hardware and software.

Some documentation on a project is not included in baselines but, nevertheless, needs to be managed and controlled to ensure that the changes are made in organized manner and that the current version is always known and available. Examples of such items are project plans (such as the configuration management plan, quality plan) and internal project procedures (such as inspection procedures).

- Repositories—One or more repositories, with appropriate access controls and procedures for backup and recovery.

- Version and build control—Version control provides unique identification of each version of a configuration item and the ability to recreate any version, and should support sequential progressions (version B supersedes version A) and branching (versions C and D are concurrently valid in different scenarios). Build control ensures valid combinations of components and versions, from subassemblies to the entire system, as well as the ability to recreate any build.

- Baselines—Point-in-time collections, of specific versions of items, which become the reference points for subsequent change management. A baseline represents a formal agreement between the customer and CMS

- Change management—Controls to ensure that the system does not diverge from its baselines without authorization and that the system includes all authorized changes. The change review and approval process should not be artificially bureaucratic.

- Status reporting—Information that is collected includes the physical characteristics of items and the types, volumes, and rates of activity. Reporting can be at detailed and rollup levels. Typical types of analysis compare actual to plan, identify trends, and monitor risk indicators.

- Configuration audits—Periodic verification that configuration management is working correctly.

Configuration management supports and overlaps with the activity sometimes referred to as document and data control, which ensures that versions are archived, that change histories are maintained, that current versions are distributed to all points of use, and that obsolete versions are removed from points of use

Why has Configuration Management?

Effective configuration management prevents situations in which

- The latest version of a deliverable or document is unknown or unclear.

- No one is sure about which components and versions belong in build.

- No one is sure about which components and versions are in build.

- The build is missing components, contains extra components, or contains wrong combination of versions.

- The build does not meet all authorized requirements or is missing authorized changes.

- No one is sure about which authorized changes are in build.

- The build contains unauthorized or undocumented changes.

- You cannot revert to previous build.

- Someone is using the wrong compiler.

- Team members are using wrong hardware or test scripts for unit testing, integration testing, or performance testing.

In addition, configuration management reporting provides important progress indicator and risk management data. For example:

- Number and sizes of components are a rough gauge to track implementation progress.

- Rates and trends of problem reports, approved changes, and check-ins give insight into stability.

- Types of problems reported and enhancements requested give insight into maturity.

- Unplanned high or low concentrations of problem reports flag components that may need a change in resources or approach.

Overview of CM Activities

This section of the guideline describes configuration management in terms of activities grouped into a number of functional areas. The following table lists the functional areas in the order they are presented in the document, with their component activities. For each activity, the table shows when you perform the activity—during project planning, during startup, as a recurring or ongoing activity in the course of the project, and/or after issuing a release

| # | Functional Area | Planning | Startup | Recurring/ Ongoing |
| --- | --- | --- | --- | --- |
|  | Setting Up a CM Program |  |  |  |
| 1 | Define the CM Process | X |  |  |
| 2 | Define CM Data Collection and Reporting Process | X |  |  |
| 3 | Specify Vendor and Subcontractor CM Requirements | X |  |  |
| 4 | Select and Install CM Environment | X | X |  |
| 5 | Set Up Repositories and Supporting Procedures |  | X |  |
| 6 | Organize the CM Team |  | X |  |
|  | Configuration Identification |  |  |  |
| 7 | Define Project Baselines |  | X |  |
| 8 | Select Configuration Items |  |  | X |
|  | Change Management |  |  |  |
| 9 | Document Change Requests/Problem Reports |  |  | X |
| 10 | Analyze Change Requests/Problem Reports |  |  | X |
| 11 | Approve and Schedule Change Requests/Problem Reports |  |  | X |
| 12 | Track System Changes |  |  | X |
|  | Configuration Control |  |  |  |
| 13 | Maintain Repositories |  | X | X |
| 14 | Control Versions |  |  | X |
| 15 | Create Builds and Releases |  |  | X |
| 16 | Baseline the Configuration |  |  | X |
|  | Status Accounting |  |  |  |
| 17 | Report Change Status |  |  | X |
| 18 | Report Configuration Status |  |  | X |
| 19 | Report CM Activity |  |  | X |
|  | Configuration Auditing |  |  |  |
| 20 | Establish Audit Approach | X |  | X |
| 21 | Conduct an Audit |  |  | X |
| 22 | Respond to Audit Findings |  |  | X |

Change Control Board

One key feature of change management is an authorizing agent, representing major stakeholders, to approve or reject proposed changes.  Examples of authorizing agents include Project Managers (PM), and CCB.  CM Procedure uses the term CCB in a generic sense to mean any authorizing agent.

Depending on the project requirement and client desire the CCB may be composed of the CMS. PM and one client representative or a group of various roles from CMS, the client and other affected groups. For Dual shore projects, the authority or control of configuration management mostly lies with onsite team; however CCB has the appropriate representation of CMS.

Configuration Identification

Configuration identification is the process of identifying and describing the items that comprise a system at specific points in time.  It has two parts:

- Defining project baselines.  This provides an agreed-to, point-in-time view of the system or project.  That is, a description of the decomposed system at defined points in time (usually at the conclusion of project phases such as requirements, design, development, etc).

- Defining configuration items, components and units.  This provides a hierarchical view of the system by means of a progressive decomposition into those subordinate entities that need to be managed through project phases (such as requirements, design, development, etc).

Project Baselines

Review the Project Management Plan, the standard project life cycle, client requirements and any existing standards or practices for establishing baselines at the account or business unit.

Following are some of the criteria when Baselines can be established:

- When project makes a delivery

- On completion of Milestone

- On Completion of Phase

- On Completion of iteration

- On Product Release

Following are some of the recommended baselines:

Development Project:

- Requirements Baseline:  Defines the scope of the project and serves as the input to design activities by detailing required business functionality.  It may form part of the ‘Contractual Baseline’ for the project.

- Design Baseline:  Serves as the design to which the system will be built to satisfy the requirements.  The design is defined such that it permits unit design, coding, testing, etc.

- Product Baseline:  Defines the end product as built by the project team and accepted by the client (including documentation). This is the final Baseline that exists at the end of testing.

- Operational Baseline:  Establishes the reference point for operations and maintenance.  This is the end product at installation and reflects the product that is deployed to the sites.

Maintenance Project:

- Current Product Baseline (Baseline prior to start of maintenance)

- Major release in the project: It will include

#### All the PCRs for Enhancement/modification

#### All the PCRs/SRs for defects fixed since last release

Conversion Project:

- Conversion Strategy baseline: define the conversion strategy and the client requirement for conversion.

- Source baseline: It includes source codes and documents, which need to be converted. Usually base lined before the conversion project starts.

- Converted baseline: Defines the converted product, which is ready for testing.

- Tested baseline: Defines the end product, when it is tested and ready to send to client for acceptance testing.

- Accepted baseline: Defines the end product, which is tested and accepted by client. It is the final baseline that exists at the end of conversion.

After selecting the baselines for the project, next step is to prepare baseline definitions by identifying:

- The baselines to be established;

- The contents to be captured in each baseline;

- The approval authority for subsequent changes;

- The point at which the baseline will be established.  Have the baseline definition document reviewed and approved by the client.

Identification of Configurable Items

The key criterion for selection of configuration Item is “Item which has potential for change during project life cycle”. Following are some other factors, which should also be considered while selecting CIs:

- Item has a small and well defined set of interfaces or relationships with other Configuration Items.

- Item is used in different computer systems (software).

- Item requires a separate identifiable set of disciplines to define, develop, construct, or deliver.

- Item is operationally independent from the user’s point of view, even if it operates on the same computer as another item (for example, preprocessing versus post-processing functions, order processing versus invoicing, off-line versus on-line functions, application versus diagnostic software).

- Item is provided by a single source, such as the development group or a customer.  Major system components to be purchased through a subcontract are normally treated as separate Configuration Items.

- Item has a different schedule for acquisition, development, testing, or delivery.

- Item is a distinct category, such as applications, disk subsystems, operating systems, compilers, or database management systems.

- Item, as a single entity, requires separate maintenance, training, and logistical support.

- Item is the largest entity that provides adequate client and CMS management visibility into the development process.

- Item is critical with respect to safety, security, or reliability.

- Process Elements – Templates and checklists, which are tailored form Organizational Process India or any template or checklist prepared by project, should be identified as CI.

- Items provided by customer for meeting project requirements will be identified as Configurable Item.

Type of Item can be any of the following regardless of the fact weather they are used within the project or supplied by client/contractor.

- Documents

- System

- Program

- Tools

An Identification scheme should be defined for each CI. An example of Identification Scheme is given below:

| Type of Element | Identification Scheme | Example |
| --- | --- | --- |
| System | [System name].System Release].[Release Date-mmyy] | INVOICE.3.0706 |
| Developed Software | [CI Name].[Release].[Patch] | [Program name].3.1 |
| Document | Document name and version plus date | CM Plan v2.1, 7/12/13 |

Type of Configuration Control: Depending upon the requirement of project different type of control are maintained for CIs

- Not Managed/Not Controlled – Work Products used as an aid to complete the project but are not critical to the project. This type of document is listed in Data management section of CM Plan and managed through the procedure defined in CM Plan.

- Managed – Work Products that are version numbered but not critical to the project. These items are also identified on the CI List.

- Managed and controlled – Work Products that are version numbered and placed in a protected library for safekeeping.  These work products are critical to the project. These items are also identified on the CI List.

Full CM Control

In addition to the above Managed and Controlled procedures full CM control means the CI requires CCB approval. Documents identified as deliverables will require full CM control and will also require an internal review and approval prior to delivery to the client.

Customer Supplied Items

- Items provided by customer for meeting project requirements will be brought under configuration control.

Example of Project Requirement, for which customer may provide any items:

- All deliverables

- Analysis

- Designing

- Coding

- Testing

- Delivering

Examples of items which customer can provide to meet above mentioned project requirements:

- Bulletins

- Any items which can explain requirement.

- SRS

- DDD

- Test plan

- Test cases

- Estimation

- Any tools

- All such items identified as part of CI in CM plan.

- Whenever project baselines are performed, these items are also base lined.

- Some of the items might be time bound. Those items must be formally returned after the time is over.

- At the closure of the project all such items must be identified for return.

Naming Convention

All projects and Products of CMS will follow this guideline for naming convention or they will define the naming convention for their project/product. In any project is following naming convention provided by client they will continue to follow the same and provide reference of that document in PMP

Naming Convention for Project Documents

Following are the standard guidelines to be adhered in naming the various artifacts. All names would be derived from the project name and the purpose/name of the artifact. It would further be appended by version tag if no CM tool were used in the project. If project is using Subversion or any tool, version no will be taken care by tool. Guidelines are elaborated for most of the identified artifact.

<PROJECT NAME> <PURPOSE/NAME> <VERSION>

<PROJECT NAME>		Mandatory

<PURPOSE/NAME>		Mandatory

<VERSION>

For detailed examples refer ANNEXURE A “Naming Convention worksheet.”

PURPOSE/NAME/TYPE:

Purpose or Name of each artifact needs to be reflected in its name so that it’s easy to identify and organize similar artifacts thereby helping in easy information retrieval. For a complete list of CIs/Non-CIs and purpose/type

Naming Convention for Tailored template or checklist

If project is modifying any template or checklist from Organizational Process its naming convention will be as follows:

<Artifacts name>-<Project Name>-VER<version no of Artifacts in Organizational Process>

Naming Convention for New template or checklist

If project has designed any new template or checklist, naming convention will be as follows:

<Artifact name>-<Project Name><Purpose>

Storing Configuration

The project team shall define the types of libraries required to be maintained in the project and maintain using configuration management tools. Following are indicative types of libraries, which may be maintained by the projects:

- Work-in-process (WIP) library i.e. with working person/in specified environment.

- Test Library under the project Team i.e. in test environment.

- Release Library with Team Leader.

Details of Library should be mentioned in CM Plan.

The procedure for backup and recovery also need to be detailed.

Version Control and Promotion

Version control takes place within the context of CM environment. Version control can be envisioned as taking place on two levels:

- Horizontal (each time a controlled element is changed, a new version of that element is created). This versioning takes place within a single level of the repository on what can be thought of as an individual “file.” Software should be controlled at the individual program level, physical inventory at the lowest replaceable unit level, and documentation at varying levels, depending on the size and structure of the document. At a minimum, the work products that make up any documentation should be under version control.

Most software CM tools impose version control at the file level, making this activity automatic and nearly transparent to the users. As each controlled element is changed, a new version is created. If your CM environment does not provide automatic version control, you need to uniquely identify each version manually as it is placed in the repository. (Instances of CM environments that do not provide automatic version control should be rare, and confined to non-electronic repositories.)

- Vertical (based on certain criteria, the elements are promoted from one level in the repository to the next). As the elements progress up through the levels, different controls are applied. Each level has different criteria that an element must meet before being promoted to that level. As elements are promoted up through the repository, they are integrated into larger and larger elements, such as configurations, builds, and releases.

When an element is promoted to a new level, control over changes will alter as well. For example, developed software at the integration testing level cannot be changed unless a Change Request/Problem Report is written and the change is approved, implemented and tested at the development level, and promoted back up to the integration testing level.

- The criteria for promotion and the processes to be followed may be dictated by the tool to a limited degree. It is advisable to establish standards for checking in new versions, to capture information such as the reason for change. This provides an audit trail should another team member be required to work on the element.

- Any element that is shared or that has been made available for reuse should be under version control to ensure that changes are communicated to the owners of all affected configuration elements.

- Once an element is base lined, do not allow check-ins or promotions without CCB authorization or as defined in Change control section CM Plan.

Build Configuration

Elements of a system are integrated into releases before being turned over to another organization, such as for testing or for delivery to the client. The process of creating a build is the same, the only difference being that a build may exist for internal purposes and may not be provided to the client.

Perform the following steps when creating a release:

- Prepare a Turnover Package to document the elements to be included in the release, provide instructions on how to construct the release, and provide testing data to verify that the release has been constructed properly. The Turnover Package is completed by those responsible for the build. Large complex releases could involve multiple Turnover Packages; for example, there could be one Turnover Package per CI, or the release could be delivered in increments.

- Verify that all inputs are present. Perform integration according to the build instructions contained in the Turnover Package. If problems are encountered, document them in Problem Reports and resolve them.

- Verify consistency of the as-built configuration with the as-submitted elements (if this is not done automatically), and test the build. The purpose of this testing is to verify that the build process was successful, that all the requisite pieces have been included, and that they function together at a high level. If testing uncovers problems, document them in a Problem Report and submit it to the change management process. Build problems can range from a missing file to incorrect build instructions or to incorrect versions being submitted for promotion.

- When you are satisfied that the release is ready for its intended use (such as prototype exposure, testing, or deployment), create supporting documentation (such as Release Notes), and make it available to the intended users. Notify all affected parties of the changes since the last release and either distribute the configuration or provide instructions on how to obtain and install it.

- Schedule periodic builds and collect non-emergency changes for integration during the next build. For an emergency change, arrange for an emergency (unscheduled) build. Emergency builds have all the same precautions and safeguards as non-emergency builds.

- Schedule builds around ongoing development, operations, or maintenance—preferably during off-hours—with the goal of minimizing the impact on those activities. Coordinate with other project personnel, with operations personnel, and with the user to avoid ill effects from other activities that might affect the build environment (such as an operating system update) and to avoid interfering with critical activities.

Base lined Configuration

The physical act of establishing a baseline involves little more than labeling a given configuration or set of configuration items as a baseline. The implications of establishing a baseline, however, need to be understood.

In effect, base lining sets a state switch that will require all future changes to the content of the baseline to be authorized in accordance with project procedures. Base lining requires notification of all stakeholders and can also occasion deliveries and special reports tied to contractual requirements.

Base lining can have repository size implications. Depending on your CM environment, base lining may cause the base lined entity to become the “master copy” which is stored in its entirety, with subsequent changes stored as “deltas” against this master copy, rather than each and every update being stored as an entire copy.

Establish baselines at predefined points in the life cycle. Because most baselines are tied to major milestones, it is often advisable to stop accepting changes as the time to create a baseline approaches. This is colloquially referred to as “chilling” a configuration. Chilling allows you to subject the configuration to preliminary auditing and verification with sufficient time to correct problems if necessary before the baseline is established.

Once an initial baseline is established, the change management process should be initiated, establishing the Change Request/Problem Report as the mechanism for requesting and authorizing changes to the baseline.

The criteria for establishing a baseline will vary according to the nature of the baseline, the client involvement, and the project processes. For example:

- Requirements Baseline—Client approval with program or project management concurrence initially, approved Change Request thereafter.

- Design Baseline —presented to the customer a minimum of three times in workshop or lab setting with no requested changes.

- Operational Baseline—Change Request approved by CCB or authorizing agent.

Configuration Status Accounting

Status accounting consists of the set of activities associated with periodic reporting on the status of a configuration and the changes to that configuration. It uses data collected during other CM activities and during development and testing activities to present information about the current state of the system under development or in maintenance. Using information collected during all CM activities, CM status accounting provides snapshots and reveals trends for change requests, configuration items, and CM activities such as builds.

CM status reporting includes metrics to support project tracking and estimating. The format and timing of reports varies according to the type of information being reported and audience needs.

Information from CM status reporting is essential not only for CM process improvement but also for quality management and project monitoring and control. Internal and external CM reports on the contents of configuration items and builds are an important part of delivery documentation. Information about build contents and change request activity helps project managers and other stakeholders monitor product completeness, stability, and quality and to estimate future activities.

- Furnish CM status reports periodically or on demand to the project manager and other configuration stakeholders.

- Base the contents, timing, delivery medium, and format of each report on its purpose and audience. Contractual requirements and organizational policies define your minimum rules for reporting. Satisfy these, and then determine whether any additional reporting expense is justified for risk management.

- Identify the source of the data that goes into each report field. Be sure to specify any special materials (such as paper forms) or technology (such as equipment or software) that are needed, and include them in the schedule.

- Archive all CM status reports in a controlled-access project data library

Configuration Auditing

Configuration auditing is a technique designed to confirm that what you plan to deliver is what you actually deliver, and that your CM practices have been followed. Configuration audits are often specified by the client and may be either witnessed or conducted by the client.

Audits give you confidence that you are delivering what you intend to deliver, and they confirm your starting point for the next stage of development or for maintenance. You must know that you have the right versions of the right elements and that you have all the necessary elements before you turn the system over to the client and proceed into maintenance or move on to the next release. The decision as to whether a product is ready to be delivered may be based, in part, on these audit results.

Audits give you the opportunity to resolve problems internally before turning a product over to the client. For example, the effort of conducting an audit that discovers that the CD-ROM containing the latest release of your end product is missing an element or contains an incorrect version of the software is far less significant than the contractual and client relationship ramifications of delivering a system that cannot be installed or operated.

Type of Audit

- Functional audits confirm that a product performs as required. They typically involve an examination of the test results against test plans to verify that the tests were executed as planned and an examination of test results against the product’s requirements to verify that the demonstrated functionality is consistent with the required functionality. This audit should be conducted before a product is released to the client.

- Physical audits confirm that the product is consistent with its documentation. It examines the as-built version of a product (or CI) against the technical documentation that defines it to verify that the product and its documentation are consistent, all authorized changes have been made, and no unauthorized changes have been made. This audit should be conducted before a product is released to the client. Physical audits may also be conducted on a build or release basis and prior to establishing any baseline.

- Process audits confirm that the CM process is being followed. These audits focus on the processes being used rather than on the products being produced. They examine the manner in which the CM activities are performed against the documented procedures. These audits should be conducted on a regular basis during the course of a project or program to allow for problem identification and corrective action.

SQA will conduct the Process audit and Physical Audit for the project. Functional audit will be conducted as per functional Audit checklist mentioned in release procedure. SQA will conduct the Physical Audit as per periodicity mentioned in Project plan and use the Physical Audit finding report template for the Audit. Project Manager will track the Audit findings to closure.

Configuration Management Milestone

Following are some example of Configuration Management Milestone

- Configuration Items identification

- CM training to team if required

- Planning documents baselined and put under Configuration control

- Requirement Document Approved for base lining

- Requirement Document baselined

- Product Baseline archived

- Product Baseline transferred to Software support

Configuration Management Tools

Most of the routine activities associated with configuration management are recurring in nature and which can easily be automated. The need for automated tools increases with the size and complexity of the project. The CM tools selected for use by project need to be compatible with the environment in which the development or maintenance is to take place.

For Client server / Microsoft:

- Visual Source Safe

- Clear Case

Generally all configuration tools will follow these steps:

- Login

- Check in

- Check out

- Compare and merge mechanism

- Handles files and projects

- Purge support

- Roll back support / Get Latest

- Sharing and branching

- Change of Password/ Security

- Version control

Stakeholder’s Matrix

| Activities |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Customer | Delivery Head | Project Manager | Dev owner | SQA | Configuration controller | Test Manager |
| Develop Configuration Management Plan |  | A,S | R |  | C,S | C,S |  |
| Establish Configuration control | S |  | A |  | C,S | R | S |
| Perform configuration audit |  | I | R |  | S | S | I |
| Configuration status reporting | I | I | A |  | C | R | S |

Definition:

| R | Responsible | Person who owns the problem/project |
| --- | --- | --- |
| A | to whom R is Accountable | He or she must sign or approve the work before it is OK |
| S | can be Supportive | Can provide resources or can play a supporting role in implementation |
| C | Should be Consulted | has information and/or capability necessary to complete the work |
| I | Should be Informed | must be notified of results, but need not be consulted |

Glossary

Baseline:  A document or set of documents and associated products (for example: source code, hardware, design documents, test plans, requirements documents, etc.) that serve as a complete description of the project or system at a point in time.  A Baseline provides an agreed-to, point-in-time view of the system or project.

Baseline Configuration:   Refers to labelling a given set of configuration Items and components as a baseline. From that point onwards, all future changes to the content of the baseline have to be made by the established change management process.

Baseline Record:  Identifies the baselines to be established, the contents to be captured in each baseline, the approval authority for subsequent changes, and the point at which the baseline will be established.

Build:  An operational version of a software system or component that incorporates a specified subset of the capabilities the final software system or component will provide. Very similar to a release except that it may exist for internal purposes and may not be provided to the client.

Change Control Board (CCB):  A board comprising client and TECHNO BRAIN representatives established to approve, modify, reject, defer and schedule Change Requests/ Problem Reports (i.e. a group of people responsible for and empowered to evaluate and make decisions that affect established baselines).  In some cases, the Change Control Board is also referred to as the Configuration Control Board.

Change Management:  The process of controlling changes to the system or project to ensure that only authorized changes are applied (i.e. managing changes to project baselines).  It involves requesting changes, analyzing the impact and feasibility of the changes, approving the changes before implementation, and tracking the changes through completion.

Change Request/ Problem Report:  A mechanism for describing a problem or requested enhancement and for capturing information about its solution and disposition.  It may be in hardcopy or electronic form.

Configuration Auditing:  A technique designed to confirm that what you plan to deliver is what you actually deliver, and that your configuration management practices have been followed.

Configuration Control:  The means by which a project controls, manages, and maintains a historical trail for hardware, software, documentation, work products, and any other documents that are important to project operation.

Configuration Management:  A discipline applying technical and administrative direction and surveillance to identify and document the functional and physical characteristics of a configuration Item, control changes to those characteristics, record and report change processing and implementation status, and verify compliance with specified requirements.

A discipline applying technical and administrative direction to identify, control changes, record and report the status of, and audit the configuration Items associated with a baseline.

Configuration Management Plan:  Identifies the system configuration; details how changes to it will be controlled; and how its integrity will be established, maintained, and verified throughout the project’s life cycle.  The Configuration Management Plan is a subset of the Project Management Plan (PMP).

Identification Scheme:  A scheme for uniquely identifying each configuration item, component, and configuration unit.  The scheme ensures that all stakeholders are always clear as to which element and which version of the element are being discussed, developed or delivered.

Release:  Represents a substantial grouping of work representing components to be developed, integrated, and deployed at the same time.

Repositories:  Repositories are basically controlled and managed inventories/ libraries/ storage areas for software, hardware, documentation, and configuration management records.  Repository features include unit check out/ in, version control, and authorized promotion to defined project life cycle stages.

Status Accounting:   Consists of the set of activities associated with periodic reporting on the status of a configuration and the changes to that configuration.

Version Control:  Version control entails identifying different versions of configuration items, components, and configuration units, and maintaining their logical relationships.