Estimation Guidelines

(Function Point Analysis)

Revision History

| Version Number | Creation/Revision Date | Prepared /Updated By | Reviewed By | Approved By | Change Description |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 18.04.2023 | Rajashree M. | Jayanta C. | Jayanta C. | Baseline Version |

Table of Contents

1	Objective	4

2	Scope	4

3	Purpose	4

4	Acronyms and Abbreviations	4

5	Introduction	5

5.1)	What is a ``Function Point''?	5

5.2)	Important introductory FPA notes	5

5.2.1).	Measured from the user's perspective	5

5.2.2).	Technology-independent	5

5.2.3).	Low cost	6

5.2.4).	Repeatable	6

5.2.5).	Work well with use cases	6

5.3)	Other useful information	6

5.4)	FP data repositories	6

5.5)	A brief history	7

5.6)	Overview	7

5.6.1)	A simple five step counting process	7

5.6.2)	Details on the  Data and Transactional Functions	8

5.6.3)	Five standard "functions"	8

(1) Data Functions - Internal Logical Files (ILFs)	9

(2) Data Functions - External Interface Files (EIFs)	10

(3) Transaction Functions - External Inputs (EI's)	11

(4) Transaction Functions - External Outputs (EO's)	13

(5) Transaction Functions - External Inquiries (EQ's)	14

5.7)	Example:  SAMPLE COUNT	16

Step 1: The type of count	16

FPA Step 2: Identify the scope and boundary of the count	17

Step 3: Determine the unadjusted function point count	17

Step 3a: Determine the count resulting from ILF's	18

Step 3b: Determine the count resulting from EIF's	22

Step 3c: Determine the count resulting from EI's	23

Step 3d: Determine the count resulting from EO's	32

Step 3e: Determine the count resulting from EQ's	32

6	The Value of Counting Function Points	34

7	Overall Summary	37

Objective

Most practitioners of Function Point Analysis (FPA) will probably agree that there are three main objectives within the process of FPA:

- Measure software by quantifying the functionality requested by and provided to the customer.

- Measure software development and maintenance independently of technology used for implementation.

- Measure software development and maintenance consistently across all projects and organizations.

In working towards objectives 2 and 3 above, several organizations have created large repositories of FP counts that cross projects, technologies, and organizations. These repositories can be an invaluable tool for your first estimation efforts, because it lets you compare your project to similar projects that have been developed by other organizations around the world.

Scope

This procedure is applicable to all the projects managed and controlled at ************* Ltd.

Purpose

The purpose of this guideline is to describe the steps and procedures used in developing a software estimate. These guidelines are intended to be a generic product which can be applied to almost any project anytime during its life cycle.

Acronyms and Abbreviations

| FPA | Function Point Analysis |
| --- | --- |
| ILF | Internal Logical File |
| EIF | External Interface File |
| EI | External Inputs |
| EO | External Outputs |
| EQ | External Enquires |
| RET | Record Element Type |
| DET | Data Element Type |
| FTR | File Type Reference |
| GSC | General System Characteristic |
| VAF | Value Added factor |
| LOC | Line of Code |

Introduction

Function Points (FPs) were introduced by Alan Albrecht of IBM 25 years ago, they remain largely unknown by most developers today.

Understanding FPA helps take the fear out of tasks like software development cost estimating. Additionally, it can also serve as an aid in measuring and improving product quality as you begin to understand critical metrics such as project velocity and defect ratio.

### What is a ``Function Point''?

Simply stated, function points are a standard unit of measure that represents the functional size of a software application. In the same way that a house is measured by the square feet it provides, the size of an application can be measured by the number of function points it delivers to the users of the application.

A good example is when I had my house built two years ago. I worked with a very straightforward home builder and he basically said ``Al, you have two choices here. First, how many square feet do you want to build? Second, what quality of materials do you want to use?'' He continued ``Let's say that you want to build a house that is 2,000 square feet. If you want to use cheap materials we can build it for $80 per square feet. That's $160,000. If you want to go top of the line then you're looking at more like $110 per square foot, and that's $220,000. What would you like?''

### Important introductory FPA notes

The following are the key points about FPA process

### Measured from the user's perspective

The size of the application being measured is based on the user's view of the system. It is based on what the user asked for, not what is delivered. It's based on the way the user interacts with the system, including the screens that the user uses to enter input, and the reports the users receive as output. Finally, it's also based on their understanding of the data that needs to be stored and processed by the system.

### Technology-independent

As mentioned in the objectives section, FPA is also technology-neutral. It does not matter what technology is used to build the application. It doesn't matter if it's a Web application written in Java, PHP, ColdFusion, or .Net; or a client-server app written in Java, Delphi, VB; or even an AS/400 RPG application. Just show me your screens and your data tables and I'll derive ``number of function points'' from there.  The screens and data tables can even be used in function point analysis.

### Low cost

Adding FPA to your software development portfolio is also very easy. Historically, adding the process of counting FPs to your development process results in a cost increase of only 1%.

### Repeatable

Studies have shown that multiple function point counters can independently count the same application to within 10% accuracy of each other. Repeatability is very important, because without it we could not begin to trust the data from the hundreds of applications that are stored in repositories around the world.

### Work well with use cases

This process works extremely well with use cases, and can even work with the concept of ``stories'' in Extreme Programming.

### Other useful information

For better understanding of the function points, the following is the background of FPAs

- Large user group

A large user group known as IFPUG (http://ifpug.org) is responsible for carrying the FP torch. IFPUG is a non-profit, member-governed organization, consisting of over 1,200 members in 30 countries around the world. As the time of this writing version 4.2 of the IFPUG specifications for counting FPs (referred to as the Counting Practices Manual) has just been released.

- ISO Standard

The ``Unadjusted FP Count'' of IFPUG v4.1 is now an ISO standard.

- De-facto standard

In addition to being an ISO standard, FPs are used as the de facto standard for cost estimating applications like Cocomo II, Construx Estimate, and other estimating packages.

- Certified Function Point Specialist, or CFPS

A CFPS is a person who has passed the official IFPUG certification test. The CFPS designation must be renewed every three years.

- Counting Practices Manual, or CPM

The CPM is the official manual created and distributed by IFPUG. It details the official counting rules used by CFPS practitioners. These rules help to keep counts consistent from one CFPS to another. Version 4.1 of this manual is over 300 pages in length.

### FP data repositories

Because many companies have been using FP information for quite some time, there are several large repositories of project data, where companies have combined FP counts along with other information, such as tools used, man hours, and overall project cost. With accurate counts and other accurate data, you don't have to feel so along when making those all-important project estimates.

### A brief history The following table shows a brief history of function points, beginning with the introduction of the concept by Alan Albrecht in 1979. 1979; FPs introduced by Alan Albrecht. 1984; First FP guidelines. 1986; First IFPUG Board of Directors. 1994; CPM Release 4.0. 2003; ISO standard. Table 1: A brief history of Function Point Analysis

The benefits of Function Point Analysis

FP helps organization to run successful software development business, including;

- The ability to accurately estimate:

  - project cost

  - project duration

  - project staffing size

- An understanding of other important metrics, such as:

  - Project defect rate

  - Cost per FP

  - FP's per hour (what I refer to as ``velocity'')

  - The productivity benefits of using new or different tools

### Overview

This section describes an overview of FPs;

### A simple five step counting process

To start at a high level, there are five steps in the process of counting FPs. They are:

- Determine the type of count.

- Identify the scope and boundary of the count.

- Determine the unadjusted FP count.

- Determine the Value Adjustment Factor.

- Calculate the Adjusted FP Count.

I'll introduce steps 1, 2, 4, and 5 during our sample count, because they are most easily introduced by using an example. At this point I'll get into the heart of step 3 in our process, because this is where the actual FP counting takes place. At this point FP practitioners look at a software application in terms of five standard functions.

### Details on the  Data and Transactional Functions

This section provides more detailed information and definitions on the five Data and Transactional Functions. Before getting into the details of the five functions there are several terms that you need to understand, because they'll be used in each of the subsequent definitions. These are taken directly from the CPM.

Important terms and definitions used in describing the five functions

- User identifiable

This term refers to defined requirements for processes and/or groups of data that are agreed upon, and understood by, both the users and software developers.

- Control information

This is data that influences and elementary process of the application being counted. It specifies what, when, or how data is to be processed.

- Elementary process

An elementary process is the smallest unit of activity that is meaningful to the user. An elementary process must be self-contained and leave the business of the application being counted in a consistent state.

- Data Element Type, or DET

A data element type is a unique, user recognizable, non-repeated field. This definition applies to both analyses of data functions and transactional functions.

- Record Element Type, or RET

A record element type is a user recognizable subgroup of data elements within an Internal Logical File or External Interface File.

### Five standard "functions"

In counting FPs there are five standard "functions" that you count. The first two of these are called Data Functions, and last three are called Transaction Functions. The names of these functions are listed below.

- Data Functions:

  - Internal logical files

  - External interface files

- Transactional Functions:

  - External Inputs

  - External Outputs

  - External Inquiries

Using this terminology, when a person that counts FPs looks at a software system, they see something like this: 
Figure 1: The view of a software application from the eyes of a Function Point practitioner.

These five functions will be discussed in greater depth in the sections that follow.

### (1)Data Functions - Internal Logical Files (ILFs)

ILF stands for "Internal Logical File". In my words, ILFs represent data that is stored and maintained within the boundary of the application you are counting. When counting ILFs you are basically counting the data functions that your application is being built to maintain.

The more precise IFPUG definition of an ILF is:

"An ILF is a user-identifiable group of logically related data or control information maintained within the boundary of the application. The primary intent of an ILF is to hold data maintained through one or more elementary processes of the application being counted."

Furthermore, for data or control information to be counted as an ILF, both of the following IFPUG counting rules must also apply:

- The group of data or control information is logical and user identifiable.

- The group of data is maintained through an elementary process within the application boundary being counted.

Examples of ILFs

Samples of things that *can* be ILFs include:

- Tables in a relational database.

- Flat files.

- Application control information, perhaps things like user preferences that are stored by the application.

- LDAP data stores.

This isn't to say that all these things are ILFs, just that they can be. Function point counts resulting from ILFs

When you're counting ILFs you will constantly be referring to the two tables that follow. The purpose of the first table is to help you determine whether the ILF you're currently looking at has a complexity level of Low (L), Average (A), or High (H). You do this by going into the table knowing the number of DETs and number of RETs you have counted in the ILF, and then finding the resulting Low, Average, or High value.

For instance, suppose I counted 5 DETs and 1 RET; that would be a Low complexity table. Conversely, if I had a table with 21 DETs and 2 RETs, that would be an Average complexity table.

| RETS | Data Element Types (DETs) |  |  |
| --- | --- | --- | --- |
|  | 1-19 | 20-50 | 51+ |
| 1 | L | L | A |
| 2 to 5 | L | A | H |
| 6 or more | A | H | H |

Table 2: The ILF complexity matrix Now that you know whether the ILF under consideration has a complexity of Low, Average, or High, you'll come to this next table and determine the number of FPs that should be counted for this ILF. A Low complexity ILF is worth 7 points, an Average ILF is worth 10 points, and a High is worth 15.

Weights:

| Complexity | Points |
| --- | --- |
| Low | 7 |
| Average | 10 |
| High | 15 |

Table 3: ILF weights

### (2)Data Functions - External Interface Files (EIFs)

EIF stands for "External Interface File". In my words, EIFs represent the data that your application will use/reference, but data that is not maintained by your application.

The official IFPUG definition of an EIF is:

"An external interface file (EIF) is a user identifiable group of logically related data or control information referenced by the application, but maintained within the boundary of another application. The primary intent of an EIF is to hold data referenced through one or more elementary processes within the boundary of the application counted. This means an EIF counted for an application must be in an ILF in another application."

Again, think of this as data that your application needs and uses, but does not maintain.

Examples of things that can be EIFs are identical to the list for ILFs, but again, the big difference here is that EIFs are not maintained by the application under consideration, but ILFs are. Function point counts resulting from EIFs

Assigning an FP value to an EIF is the same as assigning one to an ILF. First, determine the number of DETs and RETs in the EIF, then do a lookup in the following table to determine whether the EIF has a complexity of Low, Average, or High.

|  | Data Element Types (DETs) |  |  |
| --- | --- | --- | --- |
| RETS | 1-19 | 20-50 | 51+ |
| 1 | L | L | A |
| 2 to 5 | L | A | H |
| 6 or more | A | H | H |

Table 4: EIF complexity matrix Then, once you know whether the EIF is considered Low, Average, or High, look in the following table for the number of FPs to count for this particular EIF.

EIF Weights:

| Value | No. or Function Points |
| --- | --- |
| Low | 5 |
| Average | 7 |
| High | 10 |

Table 5: EIF weights You'll notice that the first two lookup tables are identical, but that more FPs are assigned to ILFs than EIFs. Here's some homework for you: Can you guess why?

### (3) Transaction Functions - External Inputs (EI's)

EI stands for "External Input". Here the official IFPUG definition of an EI is as follows:

An external input (EI) is an elementary process that processes data or control information that comes from outside the application boundary. The primary intent of an EI is to maintain one or more ILFs and/or to alter the behavior of the system.

Examples of EIs include:

- Data entry by users.

- Data or file feeds by external applications.

Function point counts resulting from EI's

Allocating FPs to EIs is similar to the process we covered for ILFs and EIFs. However, in this case, instead of doing a lookup based on DET's and RET's to determine a Low/Average/High complexity, the lookup is performed using DET and FTR values. As you'll recall from the earlier definition, an FTR is a "file type referenced", so it can be either an ILF or an EIF.

As an example, suppose that you have a process that has 5 DET's, and during the processing it references an EIF named Users and an ILF named Process. You would go into the following table looking for the complexity of an EI that has 5 DET's and 2 FTR's. As you'll see from the table below, this EI is considered an "Average" complexity EI.

| FTR's | Data Element Types (DET's) |  |  |
| --- | --- | --- | --- |
|  | 1-4 | 5-15 | 16+ |
| 0-1 | L | L | A |
| 2 | L | A | H |
| 3 or more | A | H | H |

Table 6: EI complexity matrix To carry our example forward, as you can see from the following table, an Average complexity EI is worth 4 FPs.

Weights:

| Complexity | Points/Weight |
| --- | --- |
| Low | 3 |
| Average | 4 |
| High | 6 |

Table 7: EI weights

### (4) Transaction Functions - External Outputs (EO's)

External Outputs are referred to as EO's. The IFPUG definition of an EO is as follows:

An external output (EO) is an elementary process that sends data or control information outside the application boundary. The primary intent of an external output is to present information to a user through processing logic other than, or in addition to, the retrieval of data or control information . The processing logic must contain at least one mathematical formula or calculation, create derived data maintain one or more ILFs or alter the behavior of the system.

EO examples include:

- Reports created by the application being counted, where the reports include derived information.

Function point counts resulting from EO's

Allocating FP's to EO's is very similar to the process for EI's. Again, you perform your lookup using DET's and FTR's, with a resulting Low/Average/High complexity.

As an example, suppose that you have a process that you've identified as being an EO, and it has 10 DET's and references two FTR's. You would go into the following table looking for the complexity of an EI that has 10 DET's and 2 FTR's. As you'll see from the table below, this EO is considered an ``Average'' complexity EO.

| FTR | Data Element Types (DET) |  |  |
| --- | --- | --- | --- |
|  | 1-5 | 6-19 | 20+ |
| 0-1 | L | L | A |
| 2-3 | L | A | H |
| 4 or more | A | H | H |

Table 8: EO complexity matrix Weights:

To carry our example forward, using the table that follows, you'll see that an Average complexity EO has a value of 5 FPs.

| Complexity | Points/Weight |
| --- | --- |
| Low | 4 |
| Average | 5 |
| High | 7 |

Table 9: EO weights

### (5) Transaction Functions - External Inquiries (EQ's)

The last transactional function is referred to as an EQ, or External Inquiry. The IFPUG definition of an EQ is as follows:

An external inquiry (EQ) is an elementary process that sends data or control information outside the application boundary. The primary intent of an external inquiry is to present information to a user through the retrieval of data or control information from an ILF of EIF. The processing logic contains no mathematical formulas or calculations, and creates no derived data. No ILF is maintained during the processing, nor is the behavior of the system altered.

Examples of EQs include:

- Reports created by the application being counted, where the report does not include any derived data.

- Other things known as "implied inquiries", which unfortunately, are a little out of scope for this paper.

Function point counts resulting from EQ's

Allocating an FP count to EQs is very similar to the process for EIs and EOs. Again, you perform your lookup using DETs and FTRs, with a resulting Low/Average/High complexity.

As an example, suppose that you have a process that you've identified as being an EQ, and it has 20 DETs and references 4 FTRs. You would go into the following table looking for the complexity of an EI that has 20 DETs and 4 FTRs. As you'll see from the table below, this EQ is considered a "High" complexity EQ.

| FTRs | Data Element Types (DETs) |  |  |
| --- | --- | --- | --- |
|  | 1-5 | 6-19 | 20+ |
| 0-1 | L | L | A |
| 2-3 | L | A | H |
| 4 or more | A | H | H |

Table 10: EQ complexity matrix Weights:

Carrying our EQ example forward, you'll find from the table below that a High complexity EQ is worth 6 FPs.

| Complexity | Points/Weight |
| --- | --- |
| Low | 3 |
| Average | 4 |
| High | 6 |

Table 11: EQ weights

Summary

Taken together, these two data functions (ILFs and EIFs) and three transactional functions (EIs, EOs, EQs) represent the five functions that are counted in a FP count.

### Example:  SAMPLE COUNT

An introduction to our example

To demonstrate how the FP process works, the above sample application is going to be used. The application is named "FPTracker", and as its name implies, it's a tool that I use when I perform FP counts on other applications. For instance, if I came to your company to perform FP counts on your applications, I would record the data from the functions in your applications using this tool. As output, it provides some convenient reports and an analysis of the data to help keep me from making errors in my counts.

The FPTracker application consists of the following primary process areas:

- Project management, including creating, editing, and deleting projects.

- Entity management, including creating, editing, and deleting ILFs and EIFs.

- Process management, including creating, editing, and deleting EIs, EOs, and EQs.

- Process group management, which is a mechanism for grouping processes.

- Reporting, which includes several useful FP reports.

For the purposes of our example, I'm only going to cover a subset of the application. In a few moments you'll learn more about the FPTracker application by seeing the data it stores, the screens it offers, and two output reports it provides.

The counting process

As a quick review, the five steps in the process of counting FPs are as follows:

- Determine the type of count.

- Identify the scope and boundary of the count.

- Determine the unadjusted FP count.

- Determine the Value Adjustment Factor.

- Calculate the Adjusted FP Count.

In our example we're going to follow these steps precisely.

### Step 1: The type of count

The first step in our FPA process is determining the type of count for the application at hand. Function point counts can be one of three different types:

| Name | Definition |
| --- | --- |
| Development Project FP Count | Measures the functions provided to the users with the first installation of the software being delivered. |
| Enhancement Project FP Count | Measures the modifications to an existing application. |
| Application FP Count | Measures the functionality provided to users in an existing application. |

Table 12: Types of FP counts Because my FPTracker application already exists and is in production, the type of our count is an ``Application FP Count''.

That's all we have to do for Step 1. Note that this does not have anything to do with assigning points at this time. We are simply recording what type of project we are counting, because there are different summation rules at the end of the count, and they vary depending on the type of count you are performing.

### FPA Step 2: Identify the scope and boundary of the count

The second step of the FPA process is identifying the scope and boundary of our count.

The scopeof this count will be defined by the data, screens, and reports that I'm about to show you. You should not make any assumptions about any behavior that may appear to be missing.

Regarding the boundary of this application, for our purposes FPTracker should be thought of as a simple, standalone software application. Unlike a suite of applications like Microsoft Office, or a combination of applications that can be found on an Intranet or Extranet site, the FPTracker is not tied to any other applications in any way. Therefore, if I were drawing a boundary line to set off our application from others, it would be similar to the boundary line shown in the sample of Figure 1.

It's also worth noting that the purpose of this particular count is to serve as a sample count for this paper. In the real world the purpose of our counts vary, but typical examples include:

- Serving as the basis to determine the cost of this software application.

- Helping to determine the productivity rate of the development team on this project.

- Helping to determine the retail value of this software asset to our company.

Of course there could be any number of other reasons for pursuing a count like this, but this is a good list of the typical reasons.

### Step 3: Determine the unadjusted function point count

Although the first two steps are very important in setting the groundwork for your count, and specifying the scope of your count, they are usually performed very quickly, and it is the third step that really takes the majority of the FPA time, and is the heart of the count.

In this step we'll be counting the data functions and transactional functions that yield the unadjusted FP count. As you've seen, to this point we haven't been dealing with any numbers, but we're now ready to start adding them up.

### Step 3a: Determine the count resulting from ILF's In the FPTracker application the data is stored in a series of relational database tables, so we'll use those as the basis of our analysis. The following is a list of the database table names used in the FPTracker application: - Project - Entity - Process Group - Process - ProcessDETs - ProcessEntities The full listing of the fields stored in each table are shown in the following tables. These tables provide each field name, a field description, and indicator as to whether the field should be counted as a DET, and other notes/comments regarding each field. The last row of each table provides a count of the total number of DETs in the corresponding database table. Table 13: The "Project" database table Field; Description; Count as a DET?; Notes. project_id; Sequential id, system-assigned.; No; This is a technical artifact. It is not user-recognizable, and therefore not counted.. project_name; The name a user assigns to a given project.; Yes. project_type; The type of project count.; Yes. description; A description of the project.; Yes. Total DETs:; 3. Table 14: The "Entity" database table Field; Description; Count as a DET?; Notes. entity_id; Sequential id, system-assigned.; No; System-generated sequence number. Not user-recognizable.. project_id; Foreign key.; Yes; Do count a DET for pieces of data that are required by the user to establish a relationship with another ILF or EIF. Foreign keys usually fit this definition.. name; Name of the entity.; Yes. type; Type of entity (ILF or EIF).; Yes. no. RETs; Number of RETs in the entity.; Yes. no. DETs; Number of DETs in the entity.; Yes. complexity; Calculated complexity (Low, Average, or High).; Yes. Total DETs:; 6. Table 15: The "Process" database table Field; Description; Count as a DET?; Notes. process_id; Sequential id, system-assigned.; No; System-generated sequence number. Not user-recognizable.. pg_id; Foreign key.; Yes. name; Name of the process.; Yes. type; Type of process (EI, EO, or EQ).; Yes. sort_order; Order of appearance when displayed.; Yes. no. FTRs; Number of FTRs.; Yes. no. DETs; Number of DETs.; Yes. complexity; Low, Average, or High.; Yes. description; Description of the process.; Yes. Total DETs:; 8. Table 16: The "Process Group" database table Field; Description; Count as a DET?; Notes. process group id; Sequential id, system-assigned.; No; System-generated sequence number. Not user-recognizable.. project id; Foreign key.; Yes. name; Name of the process group.; Yes. Total DETs:; 2. Table 17: The "ProcessDETs" database table Field; Description; Count as a DET?; Notes. id; Sequential id, system-assigned.; No; System-generated sequence number. Not user-recognizable.. process_id; Foreign key.; Yes. sequence; Sort order, for display purposes.; Yes. description; User-supplied description.; Yes. Total DETs:; 4. Table 18: The "ProcessEntities" database table Field; Description; Count as a DET?; Notes. id; Sequential id, system-assigned.; No; System-generated sequence number. Not user-recognizable.. process_id; Foreign key.; Yes. entity_id; Foreign key.; Yes. sequence; Sort order, for display purposes.; Yes. Total DETs:; 3.

the data they represent are all ILFs (and not EIFs) because they are maintained within the boundary of the FPTracker application. That being said, you're about to see some of the complexity of FP counting.  In this particular application there is not a one-to-one relationship between the database tables and the way a user would logically view this data being stored. As an FP counter, and also the primary user of this application.    I think of the data logically being stored like this:

- Project

- Entity

- Process Group

- Process

  - ProcessDETs

  - ProcessEntities

In this case what I'm saying is that, as the user of this application, I think of the Process DETs and the Process Entities as being logical subgroups of the overall Process data. Okay, you say, but what does that matter to me as an FP counter? Let's look at how our counts would differ if we count the tables first as being separate, then second as being logically merged.

First, if I think of the these six tables as separate ILFs, because of the number of DETs they contain, each table would be considered to be a "Low" complexity table. Because each Low table is worth 7 FPs, the FP count for these six tables would be 42 FPs (6x7=42).

However, if I look at the tables from a "logical" perspective instead of the physical RDBMS layout, what I really have are four logical groups. Because of their DET and RET counts, all four of the groups are considered "Low" in complexity. So, in this case, the total count is 28 FPs (4x7=28).

Therefore, had I counted the physical implementation of the tables as opposed to a logical grouping, I would have over-counted this portion of the application by 14 FPs, or 50%. This is a good example of where a physical implementation differs from a correct, logical grouping for an FP count. Total Count Due to ILFs

To tally up the FP count due to ILFs, I've identified four ILFs, with the number of RETs and number of DETs as shown in the table below. The first three ILFs are very straightforward, and as discussed above, I believe that I have one Process ILF with three RETs: (1) Process, (2) Process DETs, and (3) Process Entities. Using the ILF lookup table shown earlier in Table 2, I see that each ILF is considered "Low" in complexity. Looking up Low Complexity ILFs in Table 3, I see that a Low Complexity table is counted as seven FPs. This gives me the total of 28 FPs as a result of ILFs.

| ILF | No. RETs | No. DETs | Complexity | Function Points |
| --- | --- | --- | --- | --- |
| Project | 1 | 3 | Low | 7 |
| Entity | 1 | 6 | Low | 7 |
| Process Group | 1 | 2 | Low | 7 |
| Process | 3 | 13 | Low | 7 |
| Total: | 28 |  |  |  |

Table 19: Total FP counts due to ILFs

### Step 3b: Determine the count resulting from EIF's

In this particular application there are no EIFs, so EIFs contribute zero FPs to the overall FP count.

However, in many applications there definitely are EIFs. Suppose, for example, that this application required the use of a file named Users, and this file was maintained by another application, but was accessed by our application. In this case the file would be counted as an EIF, using the EIF rules discussed earlier.

At this point we've finished counting data functions, and it's time to move on to transaction functions.

### Step 3c: Determine the count resulting from EI's To begin counting the transactional functions we first need to look at the user interface screens in the application. Let's look at all of these screens first, then determine which of these are EI's, which are EO's, and finally which are EQ's. Screen shots from the application Figure 2: The "New Project" screen lets users create a new project. Figure 3: This screen shows the Entities tab. From this location users can View, Add, Edit, and Delete entities. Figure 4: The "Add Entity" screen lets the user add new entities (ILFs and EIFs) to the project. Figure 5: The "Edit Entity" screen lets the user edit entities in the project. Figure 6: The "Delete Entity" screen asks the users to confirm their attempt to delete an entity in the application. Figure 7: This screen shows the Process Groups tab. From this screen users can Add, Edit, and Delete Process Groups. Figure 8: The "Add Process Group" screen lets the user add new process groups to the application. Figure 9: The "Edit Process Group" lets the user assign a new name to a process group. Figure 10: This screen lets the user delete a selected process group. Figure 11: This figure shows the Processes tab. From this location users can Add, Clone, Edit, and Delete processes. Figure 12: This screen lets the user define a new process. Note the "Description" tab. Those details are shown in the Figure 13: This screen shows the details of the Comments/Description tab. Users can optionally enter information here when creating a new Process. Figure 14: Users can use this screen to clone a Process in the application. They simply select an existing Process, then select a Clone option that leads to this screen Figure 15: This screen shows a basic Unadjusted Function Point Count report. Figure 16: This figure shows a report provided by the application called the "ILF/EIF Report". Brief process descriptions Because you haven't seen this application before, it may be hard to understand the processes in this application. Therefore,brief name and description of each process in this application is given below. Process Name; Process Description. Create a Project; This screen is displayed in Figure 2. This lets the user create a new project. Note that for the purposes of this paper I am skipping other project-related processes, including the ability to list, edit, delete, and clone projects.. Display Entity List; The list is displayed in Figure 3. This is a list of every Entity that the user has identified for the application they are counting.. Add Entity; Shown in Figure 4, this dialog lets the user add a new Entity.. Edit Entity; Shown in Figure 5, this dialog lets the user edit an existing Entity. This dialog appears when the user highlights a row in the Entity List, then selects the Edit button. Alternatively, they can double-click on the desired row.. Delete Entity; Shown in Figure 6, this confirmation dialog is displayed when a user selects a row, then presses the Delete button.. Display Process Group List; This list is shown in Figure 7. This is a list of every Process Group the user has identified.. Add Process Group; Shown in Figure 8, this dialog lets the user define a new Process Group.. Edit Process Group; Shown in Figure 9, this dialog lets the user edit an existing Process Group.. Delete Process Group; Shown in Figure 10, this confirmation dialog is displayed when a user selects a row in the Process Group table, then presses the Delete button.. Display Process List; The list is displayed in Figure 11. This is a list of every Process that the user has identified for the application they are counting.. Add Process; Shown in Figures 12 and 13, this dialog lets the user define a new Process.. Edit Process; Although not shown, this dialog is identical to screens shown in Figures 12 and 13, other than the title of the dialog. These screens let the user edit an existing Process.. Delete Process; Although not shown, this confirmation dialog is displayed when a user selects a row, then presses the Delete button. For the sake of our count, assume that it is a simple confirmation dialog, similar to the dialog for deleting a Process Group.. Clone Process; Shown in Figure 14, this dialog lets the user make a duplicate copy of a Process. This makes it easy to create new processes which are very similar to an existing process.. Display UFPC Report; Shown in Figure 15, this is a typical report that totals up the number of FPs in the application you are recording. The report is displayed after the user selects the report type from a drop-down list of reports in the Reports tab. The list of data shown in the drop-down list is hard-coded into the application.. Display ILF/EIF Report; Shown in Figure 16, this report shows the ILFs and EIFs (i.e., all the FTRs) in the application, along with their associated number of DETs and RETs, as well as their complexity level. It is selected from the same drop-down list as the UFPC Report.. Table 20: For counting purposes, we will also assume that each data-entry screen can also result in one or more error screens. For example, when a user is creating a new project, the system will display an error dialog if they do not provide a project name, because this is a required field. In the next section we'll classify each of these processes as an EI, EO, or EQ, and determine the FPs associated with each process. Function points resulting from EI's The table below lists the External Inputs in the application. It also lists the number of DETs and FTRs for each process, and the complexity that results from the number of DETs and FTRs. Process; # DETs; FTR Names; # FTRs; Resulting Complexity; # FPs. Create Project; 5; Project; 1; Low; 3. Add Entity; 7; Project, Entity; 2; Average; 4. Edit Entity; 7; Project, Entity; 2; Average; 4. Delete Entity; 4; Project, Entity; 2; Low; 3. Add Process Group; 3; Project, ProcessGroup; 2; Low; 3. Edit Process Group; 3; Project, ProcessGroup; 2; Low; 3. Delete Process Group; 4; Project, ProcessGroup; 2; Low; 3. Add Process; 9; Project, Process, ProcessGroup; 3; High; 6. Edit Process; 9; Project, Process, ProcessGroup; 3; High; 6. Delete Process; 5; Project, Process, ProcessGroup; 3; High; 6. Clone Process; 3; Project, Process, ProcessGroup; 3; Average; 4. Total:; 45. Table 21: External Inputs (EI's) in the FPTracker application

### Step 3d: Determine the count resulting from EO's

According to the rules, we have only one EO, and that is the UFPC Report. This report is considered an EO, and specifically not an EQ, because it contains derived data. More specifically, the complexity total column and the total UFPC count at the bottom of the table are derived fields, and EQs specifically cannot contain derived fields like this.

This report is actually a very difficult report for me to get right, and that's exactly why I've included it here. It's hard for me because of the rules surrounding duplicated fields in reports. Unfortunately, rather than get into all the complexity of these rules, I'm just going to state that there are at least seven DETs in this report, and they are:

- Title

- Function type

- Functional complexity

- The complexity totals

- The function type totals

- The Unadjusted FP Count

- A DET that is counted for the menu option to choose this report

| Process | DETs | FTRs | Resulting Complexity | # FPs |
| --- | --- | --- | --- | --- |
| UFPC Report | 7 | 3 | Average | 4 |
|  |  |  | Total: | 4 |

Table 22: External Outputs (EO's) in the FPTracker application

Because of the repeating fields this is a very difficult report for me. Fortunately, when I double-checked with a colleague we both came up with an Average score for this EO, even though we differed on the fields slightly. That's one of the nice things about using ranges like this; very rarely does a disagreement about the detailed rules actually affect a count.

### Step 3e: Determine the count resulting from EQ's

The table below lists the External Inquiries in the application. It also lists counts of the number of DETs and FTRs for each process, and the complexity that results from the number of DETs and FTRs.

We begin with the ILF/EIF Report. Fortunately, it's a lot easier that the UFPC Report. It contains six DETs, including the title, data function names, function type, number of RETs, number of DETs, and complexity. Looking at the report, you can also see that it retrieves information from the Project and Entity ILFs, so there are two ILFs. Implied Inquiries

The rest of the EQs in the table below are probably quite a surprise. I haven't introduced them yet, primarily because they add a little complexity to the mix. Each of the last four processes in this table are referred to as "implied inquiries". They are the almost hidden processes in an application that are easy to overlook. For instance, if you look back at Figures 3, 7, and 11, you'll see that the application has built-in lists of Entities, Process Groups, and Processes. These are the tables (JTable's to be more specific) that are contain in the Entity, Process Group, and Process tabs, respectively. Some type of query had to be performed to generate these lists, and those types of queries that result in this "view list" operation often qualify as "implied inquiries".

The Process Group drop-down list on the Add/Edit Process dialog is another implied inquiry. It took some type of query to generate that list, and again it is considered an implied inquiry.

While I'm covering this important topic rather quickly, it's important to note that other drop-down lists and tables may not qualify as implied inquiries, especially when the data they contain is hard-coded in the application. You also might not count the listing as an implied inquiry if the data could have beenhard-coded. This is an introductory tutorial, so that's all I'm going to say about this topic for now, other than the fact that I will refer you to the CPM for more specific rules.

| Process | DETs | FTRs | Resulting Complexity | # FPs |
| --- | --- | --- | --- | --- |
| ILF/EIF Report | 6 | 2 | Average | 5 |
| Display List of Entities | 5 | 2 | Low | 4 |
| Display List of Process Groups | 2 | 2 | Low | 4 |
| Display List of Processes | 7 | 3 | Average | 5 |
| Implied Inquiry - Process Group ComboBox on the Add/Edit Process Dialog | 1 | 2 | Low | 4 |
|  |  |  | Total: | 22 |

Table 23: External Inquiries (EQ's) in the FPTracker application Total Count

Now that we've finished counting the ILFs, EIFs, EIs, EOs, and EQs in the application, we add up each of the individual counts to get a total unadjusted function point count for the application. This is shown in the table that follows.

| Function Type | Complexity | Multiplier | Line Item Sub-Total | Section Total |
| --- | --- | --- | --- | --- |
| ILF | 4 Low | x 7 = | 28 |  |
|  | 0 Average | x 10 = | 0 |  |
|  | 0 High | x 15 = | 0 | 28 |
| EIF | 0 Low | x 5 = | 0 |  |
|  | 0 Average | x 7 = | 0 |  |
|  | 0 High | x 10 = | 0 | 0 |
| EI | 5 Low | x 3 = | 15 |  |
|  | 3 Average | x 4 = | 12 |  |
|  | 3 High | x 6 = | 18 | 45 |
| EQ | 0 Low | x 3 = | 0 |  |
|  | 1 Average | x 4 = | 4 |  |
|  | 0 High | x 6 = | 0 | 4 |
| EO | 3 Low | x 4 = | 12 |  |
|  | 2 Average | x 5 = | 10 |  |
|  | 0 High | x 7 = | 0 | 22 |
|  |  |  | Unadjusted Function Point Count: | 99 |

Table 24: The unadjusted function point count for the FPTracker application The total unadjusted function point count for this application (at this date and time) is 99 function points.

The Value of Counting Function Points

Okay, I showed you the "how" of FP counting, but I'd like to return to the "why" of FP counting, because I think motivation is a very important driver here. You need to asking yourself "Why should you add as much as 1% to your overall software development effort?"

My experience with FP counting has shown all of the benefits I mentioned earlier in this document. Once you have a history of developing applications and you also have FP counts for all those applications, you can now add to your software development arsenal these capabilities:

- The ability to accurately estimate:

  - project cost

  - project duration

  - optimum project staffing size

- The ability to determine other important metrics, such as:

  - Project defect rate

  - Cost per FP

  - FP's per hour (a productivity rate; I tend to refer to it as "Velocity", a term I like from Extreme Programming)

  - The productivity benefits of using new or different tools

So, the question to you is "What are these abilities worth to you?"

For me, the biggest benefit of FP counting means that my company can get into fixed-price software development projects. When a prospect says "Al, can you do this project for $100,000?" I can run around the corner, scratch some numbers on the back of an envelope, and give them a Yes or No answer. And while doing this I can be pretty well assured that the company won't go bankrupt on this project.

Why is this important? Because I've never met a developer that likes to estimate programming work, and the bigger the work, the worse is gets. I don't blame them; estimating is very hard, especially on larger projects. I've met a lot of developers, and some always estimate low, some always estimate high, and others go both high and low. As a manager, I'd much rather have some cold statistics that I can rely on in times like this, even if it's just as a point of comparison.

An example of how this works

As an example of how this works, I'm going to walk through the process that we followed recently. This involves two small phases of development on one project. On this project, the developers, project managers, users, technology, and application all remained constant. We also followed a relatively formal process, beginning with a requirements phase, which led into development, testing, and final delivery of a portion of an application.

- A first measurement

In my case I was able to start with one project that we were already developing. The project itself was small, but it was a distributed Java Swing application with an embedded database that runs on Windows, Mac, and Linux platforms, so even though the application itself was small, the degree of complexity here was very high.

The first thing we did was to finish the requirements documentation and initial prototypes for our application. Once I had this information, which included a simple, logical view of the database requirements, I was able to count the function points for this small project. We created what we thought was a fairly detailed requirements document, and the count at this time was 400 FPs.

Skipping a few details here, let's just say that the next thing we did was to develop this project. When we called the development "complete", I counted the number of FPs that were actually delivered to the users. This was 440 FPs, or a growth from the requirements stage of 11%.

At this point I also had development time information. Two developers worked on this project for a total of 540 man-hours. This comes out to be 0.815 FPs/hour (440 FPs divided by 540 man-hours). Had our customer kept a good record of time that users spent testing the application they also could have determined a metric of "Number of testing hours per FP", but they did not. IMHO, I think this would benefit them in the future, but in my role, application testing is not my responsibility, so I did not pursue this.

Although we spent 540 hours on this project, the real "calendar time" for delivery of the application was 10 weeks. This was because of several periods of down time during the development process. Therefore this project was delivered at the rate of 44 FPs per calendar week.

Depending on how you track cost information, you can also determine "Cost per FP". As I stated earlier, as an independent software development firm, we now develop complex applications like this for about $250/FP.

- Your second measurement

Because this is an ongoing project, we basically repeated the same steps on the next phase of our project. For summary purposes, here are the steps we followed:

- Develop the requirements, including an understanding of the necessary data stores and screens to be developed.

- Count the FPs.

- Supplied an estimate of the project cost, assuming another 11% gain in functionality (scope creep) during development.

- Develop the code.

- Track the amount of time people spend on the project during development and testing.

- Count the FPs again.

- Deliver useful project metrics, including:

  - Number of developer hours.

  - Number of testing hours.

  - Average number of hours per FP.

  - Elapsed calendar time, which yields something like "Number of calendar days per FP" or the converse of "Number of FPs per calendar day". This occurs when there is down time in a project, or when your development resources are not fully dedicated to the project at hand.

  - Development cost per FP.

  - Testing cost per FP.

  - Overall cost per FP (including other time for management, documentation, etc.).

  - The ratio of Requirements time to Development time, and other similar ratios.

Note that Step 3 in this example is "estimate the project cost". Because we have the same developers, users, and managers working on a different part of the same project, isn't it reasonable to assume that the project velocity for earlier phases will be the same for this new phase? For me, this is at the heart of estimating new development work with FPs. Given this scenario of having the same developers, users, and managers, and working with the same technology on the same application, I'm glad to take my chances estimating with FPs.

Now, if you suddenly change any of these factors, you can use this same information for your estimates, but you're estimate will probably vary somewhat. For instance, with our company, I've found that we can develop web applications much, much faster than we can develop Swing applications. Of course this is an over-simplification, but in general a simple web application conforming to HTML 3.2 specifications is much easier for us to develop, and hence our cost estimate and delivery times will be scaled down for this environment.

Another factor you'll be able to measure is the impact of new technology and tools on your development costs. As I mentioned, we deliver Web applications much faster than Swing applications, so a 500 FP Web application will be developed faster than a 500 FP Swing application. Although the size (amount) of functionality we're delivering to the customer is equivalent, the technology that we're using to deliver the applications is different, and for us, web applications are much less expensive.

That being said, I've found that other factors, including project managers and customers can also be a major influence on the overall development time and cost. For instance, when it comes to customers, it's much easier to work with a small team of customers that agree on what they want an application to deliver, versus a large committee with different opinions. The large committee is going to take more time during the requirements process, and IMHO is going to be subject to a larger scope creep during development.

In summary, given a little bit of time and statistics, your organization can rapidly begin applying FPs to use these same metrics. Over time, your cost and time estimates will get much more accurate. And, as you bring new technologies into your portfolio, you'll be able to look at these metrics and see the positive (or negative) correlation of new technology.

Overall Summary

The concept of Function Points was invented by Alan Albrecht 25 years ago, yet they remain a mystery to most developers today. That's unfortunate, because once you know the functional size of an application, you've opens a new door to accurate project cost estimation and other useful metrics. a

A recap of the process of Function Point Analysis shows that Function Points:

- Are measured from the user's perspective (not a developer's perspective).

- Are independent of the technology used to develop the application.

- Are low cost, adding less than a 1% overhead to your process.

- Are repeatable, as studies have shown that certified function point counters can come within 10% of each other.

- Are ``use case friendly'', because counting function points typically corresponds to processes defined in use cases.

Using Function Point Analysis helps you more accurately estimate:

- Project cost

- Project duration

- Optimum project staffing size

An accurate counting of function points leads to a wealth of valuable statistics that can be used to improve the development process, including:

- Number of developer hours per FP.

- Number of total hours per FP.

- Cost per FP.

- Number of FPs per month/week/day.

- Number of bugs/defects per FP.

- Number of bug/defect hours per FP.

- Productivity increases (or decreases) due to technology changes.

These metrics, and others like them, can be used as part of the feedback loop to improve your software development lifecycle.

For more information, visit IFPUG.org.